## Slide 1
askalpha
EXECUTIVE DELIVERY UPDATE
From working answers
to governed scale
Progress delivered. Strategic integrations. Decisions required.
DELIVERED
A governed SQL
foundation
NEXT
A controlled
business pilot
DECIDE
Priorities, ownership
and readiness
Foundation & Trust → Enterprise Integration & Efficiency → Advanced Visualization
September 2026
Notes: REVISION: MVP 2 now includes targeted enterprise integrations as well as efficiency. Genie, on-premises connectivity and Collibra are proposed workstreams; none is newly claimed as implemented.
PRIOR SLIDE CONTEXT (retained where not superseded)
Leadership update. This uses the documented accepted foundation through 2E, the 1 September architecture delta and owner decisions. Existing business-question capability is a bounded working proof of concept. The three-card summary does not imply that the governed business pilot or production rollout has already been approved. No financial return or launch date is asserted.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S1] Authoritative current-state record, updated 26 Aug 2026. ChatGPT Library file ID file_00000000794881fdbf5e728f1de30ebd. Foundation through 2E; one pilot dataset/recipe; 199 governed fields; bounded evidence and successful workflows.
[S2] Phase journey and manager summary, updated 26 Aug 2026. ChatGPT Library file ID file_00000000e57881fda2f0c1cc493a8779. Management roadmap and feature map, updated 26 Aug 2026: file_00000000212881fd8df615c438684075.
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S6] Owner-provided conversation and roadmap photographs. Preserves three delivery milestones: Foundation & Trust; Scale & Efficiency; Advanced Visualization. Latest owner direction: application-owned entity authorization with Managed Identity source access and no user-ACL synchronization; early and post-plan caching; Semantic Registry business authority; deterministic output routing; Genie future evaluation. Two-week demos are a proposed cadence, not committed release dates.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S1] Authoritative current-state record, updated 26 Aug 2026. Library file ID file_00000000794881fdbf5e728f1de30ebd. Accepted foundation through 2E; one governed pilot dataset and calculation; 199 evidenced fields. Historical delivery evidence, not a live production check.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 2
LEADERSHIP BRIEF
askalpha
Deliver the trust milestone; prepare targeted integrations.
Keep core delivery moving while clarifying the next sources, services and owners.
askalpha | executive update | September 2026
Evidence: S1–S3, S7
02
COMPLETED FOUNDATION
Safer, repeatable
answers
Secure, read-only access
Versioned metadata and validated analytical plans
One governed calculation with field-change protection
IN DELIVERY / NEXT
Governed business
readiness
Approval and change policies
Certified definitions and consistent output templates
Controlled pilot and integration discovery
LEADERSHIP ASK
Close the decisions
that unlock delivery
Pilot scope and accountable owners
Genie, on-premises and Collibra priorities
Value, privacy and operating gates
RECOMMENDATION
Complete the core pilot; qualify integrations before committing to wider rollout.
Notes: REVISION: Integration discovery can proceed alongside MVP 1; runtime integrations remain gated. The proposed workstreams do not replace approval, privacy or production-readiness obligations.
PRIOR SLIDE CONTEXT (retained where not superseded)
The completed column refers to engineering-delivered capability in the governed pilot, not enterprise-wide certification. The next column combines reported in-progress lifecycle work and later planned governance/templates/pilot work. The leadership asks are recommendations, not already approved funding or ownership.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S1] Authoritative current-state record, updated 26 Aug 2026. ChatGPT Library file ID file_00000000794881fdbf5e728f1de30ebd. Foundation through 2E; one pilot dataset/recipe; 199 governed fields; bounded evidence and successful workflows.
[S2] Phase journey and manager summary, updated 26 Aug 2026. ChatGPT Library file ID file_00000000e57881fda2f0c1cc493a8779. Management roadmap and feature map, updated 26 Aug 2026: file_00000000212881fd8df615c438684075.
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S6] Owner-provided conversation and roadmap photographs. Preserves three delivery milestones: Foundation & Trust; Scale & Efficiency; Advanced Visualization. Latest owner direction: application-owned entity authorization with Managed Identity source access and no user-ACL synchronization; early and post-plan caching; Semantic Registry business authority; deterministic output routing; Genie future evaluation. Two-week demos are a proposed cadence, not committed release dates.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S1] Authoritative current-state record, updated 26 Aug 2026. Library file ID file_00000000794881fdbf5e728f1de30ebd. Accepted foundation through 2E; one governed pilot dataset and calculation; 199 evidenced fields. Historical delivery evidence, not a live production check.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 3
DELIVERED FOUNDATION
askalpha
Completed work makes the pilot safer and repeatable.
Documented delivery through Phase 2E; verification recorded on 26 August 2026.
askalpha | executive update | September 2026
Evidence: S1, S2, S5
03
CAPABILITY
WHAT HAS BEEN DELIVERED
WHY IT MATTERS
Secure access
Authenticated users, entity permissions
and bounded read-only queries.
Constrains access and
protects source data.
Governed planning
Versioned metadata and validation
of selected data and fields.
Provides a reviewable basis
for the answer.
Repeatable logic
One approved calculation pilot
using governed dependencies.
Reduces improvisation in
important business logic.
Change protection
Checks for missing or materially
changed required field evidence.
Stops affected answers rather
than silently using invalid inputs.
Platform flexibility
A source-adapter boundary around
the current SQL execution path.
Preserves the core when
approved sources are added.
1
governed pilot dataset
1
approved calculation
199
evidenced field definitions
SCOPE MATTERS
These are accepted pilot capabilities—not a claim of enterprise production rollout.
Notes: REVISION: No additional delivered integration or production capability is asserted. Existing SQL execution support is not evidence of a working on-premises deployment.
PRIOR SLIDE CONTEXT (retained where not superseded)
Source S1 records one governed pilot dataset, one approved recipe and 199 strictly evidenced governed fields. These are not enterprise-wide coverage or 199 certified metrics. The documented accepted provider-neutral DataSourceAdapter boundary does not mean Databricks or other source integrations are live. Existing metadata-snapshot caching is not distributed result caching. No current repository state is asserted.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S1] Authoritative current-state record, updated 26 Aug 2026. ChatGPT Library file ID file_00000000794881fdbf5e728f1de30ebd. Foundation through 2E; one pilot dataset/recipe; 199 governed fields; bounded evidence and successful workflows.
[S2] Phase journey and manager summary, updated 26 Aug 2026. ChatGPT Library file ID file_00000000e57881fda2f0c1cc493a8779. Management roadmap and feature map, updated 26 Aug 2026: file_00000000212881fd8df615c438684075.
[S5] Architecture and roadmap update, updated 26 Aug 2026: file_00000000a02081fd918c3632e0a5a902. Assumption and decision log: file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution and bounded results; scale qualification remains later work.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S1] Authoritative current-state record, updated 26 Aug 2026. Library file ID file_00000000794881fdbf5e728f1de30ebd. Accepted foundation through 2E; one governed pilot dataset and calculation; 199 evidenced fields. Historical delivery evidence, not a live production check.
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 4
CURRENT DELIVERY FOCUS
askalpha
Make governed answers operationally manageable.
Extend the accepted foundation without restarting completed work.
askalpha | executive update | September 2026
Evidence: S3, S4
04
LIFECYCLE CLASSIFICATION
Implementation and independent-review evidence reported; final integration status to confirm.
VALID
NEEDS REVIEW
BROKEN
NOT APPROVED
01
Approval & renewal
Name accountable approvers.
Define renewal and change rules.
02
Certified meaning
Agree metric ownership and
Collibra metadata boundaries.
03
Consistent outputs
Use versioned templates and
fixed formatting rules.
DESIGN RULE
Templates reference approved definitions; presentation must not change business meaning.
Notes: REVISION: Collibra source-of-record and import contracts should be considered during Phase 2F.3. The runtime Semantic Registry remains the canonical published semantic snapshot. No new Collibra API or network work belongs in the pure Phase 2F.1 evaluator. Existing 2F.1 status remains reported implementation/review with final integration requiring verification.
PRIOR SLIDE CONTEXT (retained where not superseded)
The 1 September impact report supersedes older statements that all Phase 2F implementation was not started. It reports 2F.1 implemented and independently reviewed, but merge acceptance remains REVERIFY_REQUIRED. Its lifecycle classifier is default-OFF, classification-only and does not itself activate a production execution policy. The cards show next work (2F.2, 2F.3 and 2F.4), not delivery already achieved. Warn versus block for resolvable governed change is an owner decision; missing authorization and invalid required evidence must still fail closed.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. ChatGPT Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Lifecycle, approval policy, certified meaning, templates, evidence-gated relationships and acceptance conditions.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W3] Collibra developer documentation: APIs https://developer.collibra.com/api ; Output Module https://developer.collibra.com/api/guides/output-module . Checked 9 Sep 2026. Supported APIs can retrieve assets, attributes and relationships. Availability, populated metadata, credentials, permissions and enterprise approval remain to be confirmed in the relevant environment.

## Slide 5
ROADMAP AT A GLANCE
askalpha
Three milestones, with enterprise integration made explicit.
MVP 2 expands beyond efficiency; discovery can start alongside the trust milestone.
askalpha | executive update | September 2026
Basis: S2–S7 · proposed sequencing
05
NOW · IN DELIVERY
MVP 1
Foundation
& Trust
Governed approvals and outputs
Qualified core business pilot
Integration discovery in parallel
EXIT GATE
Pilot and controls accepted
NEXT · PLANNED
MVP 2
Enterprise Integration
& Efficiency
First approved on-premises source
Collibra intake; Genie if qualified
Secure caching; measurable value
EXIT GATE
Integration and value gates passed
LATER · PLANNED
MVP 3
Advanced
Visualization
Decision-ready charts and drill-down
Governed reports and exports
Adoption-led user experience
EXIT GATE
Safe sharing and adoption proven
AT EVERY MILESTONE
Security • Data trust • Answer quality • Performance • Cost • Adoption
Notes: The original three executive milestones are preserved; the second is renamed Enterprise Integration & Efficiency. This is proposed delivery packaging, not a renumbering of engineering phases. MVP 1 integrates the accepted foundation and pending 2F/2G trust controls. Genie feasibility and on-premises access discovery may run alongside it; Collibra ownership and metadata contracts belong with Phase 2F.3. Targeted runtime integration follows in engineering Phase 3 / proposed MVP 2 only after readiness and value gates. Genie is conditional, not guaranteed. An on-premises connector may move into MVP 1 only if essential to the approved pilot. Efficiency work spans later engineering phases; advanced visualization aligns with Phase 8. No milestone date or deployment is asserted.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S6] Owner-supplied conversation and previous roadmap photographs. Three executive milestones and green/white design direction. Application-owned entity authorization; service-identity source access; no mirrored user ACLs; governed semantics, templates and cache design. Photos are visual/reference material, not evidence of delivery or measured ROI.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 6
NEXT DELIVERY SEQUENCE
askalpha
Advance the core and integration discovery in parallel.
Proposed next actions; agree scope, ownership and capacity before setting delivery dates.
askalpha | executive update | September 2026
Basis: S3, S4, S7
06
1
Confirm the
baseline
Verify integration evidence and preserve accepted behavior.
ENGINEERING
2
Approve meaning
and change policy
Name semantic owners and define renewal and change rules.
PRODUCT + GOVERNANCE
3
Deliver governed
outputs
Use approved definitions and versioned templates.
ENGINEERING + DATA OWNERS
4
Qualify the
business pilot
Test answer quality, access and operating readiness.
BUSINESS + QA + OPERATIONS
IN PARALLEL
Genie feasibility • On-premises access • Collibra metadata contract
DELIVERY CADENCE
Two-week working demos proposed; release only when the required gates are met.
Notes: REVISION: The four core-delivery steps remain intact. Parallel work is bounded discovery: one Genie domain comparison, one on-premises source/access feasibility study and one Collibra metadata contract. Do not postpone the SQL-based governed pilot for optional integrations. Return an owner-backed go/no-go recommendation before runtime implementation.
PRIOR SLIDE CONTEXT (retained where not superseded)
This is a proposed executive work sequence based on the 1 September impact report, not authorization to change code or a dated plan. Detailed engineering sequence: reverify current baseline; close 2F.2 policy; certified semantic objects in 2F.3; template contracts and deterministic formatting in 2F.4; relationship impact only after governed evidence; hardening; controlled publish/rollback. AI formatting is optional and should stay disabled until approved. Delivery cadence comes from the supplied roadmap and must be agreed against capacity. Core work can proceed while integration approvals are resolved; an unapproved path cannot be used for a production pilot.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. ChatGPT Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Lifecycle, approval policy, certified meaning, templates, evidence-gated relationships and acceptance conditions.
[S6] Owner-provided conversation and roadmap photographs. Preserves three delivery milestones: Foundation & Trust; Scale & Efficiency; Advanced Visualization. Latest owner direction: application-owned entity authorization with Managed Identity source access and no user-ACL synchronization; early and post-plan caching; Semantic Registry business authority; deterministic output routing; Genie future evaluation. Two-week demos are a proposed cadence, not committed release dates.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 7
MVP 2 · EFFICIENCY TRACK
askalpha
Keep performance and cost measurable as coverage grows.
Targeted integration and efficiency are complementary—not automatic capacity commitments.
askalpha | executive update | September 2026
Evidence: S3, S5–S7
07
Reuse authorized
answers
Early lookup before AI planning.
A second cache for precise results.
Only small, bounded payloads.
Prepare common
questions
Prioritize patterns from usage.
Curate approved questions and summaries.
Release changes under review.
Publish with
control
Governed onboarding and rollback.
Named business and data owners.
Visible cost and performance.
~5 TB+
Source-data planning context—not cache size or proven capacity.
Keep large queries on the source platform; benchmark representative peak usage.
VALUE GATE
Measure response time, cost per answer and cache benefit before expanding capacity.
Notes: REVISION: Efficiency is one track within Enterprise Integration & Efficiency. No additional infrastructure or cache product is selected. Early-cache matching must be deterministic before any LLM call, include exact request parameters and authorization context, and validate entry eligibility. If a cache returns only a plan, source execution is still required; only an eligible result hit can skip the data query.
PRIOR SLIDE CONTEXT (retained where not superseded)
Two planned caches serve different purposes: an early request/template lookup must use deterministic information available before an AI call; the post-plan result cache may use a semantic plan hash. No current cache delivery is asserted. Safe keys need scope, exact request/template parameters and context, registry/recipe/template/policy/freshness identity and output semantics. Authorization precedes lookup. Cached results must be revalidated for scope and policy where applicable; a source revocation policy must be defined rather than assuming cache access bypasses platform controls. Approximately 5 TB or more is owner-provided planning context, not tested capacity. Monthly curated release is a working direction, not mandatory daily automation.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S5] Architecture and roadmap update, updated 26 Aug 2026: file_00000000a02081fd918c3632e0a5a902. Assumption and decision log: file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution and bounded results; scale qualification remains later work.
[S6] Owner-provided conversation and roadmap photographs. Preserves three delivery milestones: Foundation & Trust; Scale & Efficiency; Advanced Visualization. Latest owner direction: application-owned entity authorization with Managed Identity source access and no user-ACL synchronization; early and post-plan caching; Semantic Registry business authority; deterministic output routing; Genie future evaluation. Two-week demos are a proposed cadence, not committed release dates.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 8
STRATEGIC INTEGRATIONS
askalpha
Three integrations address three different business needs.
All have high strategic value; first implementation follows pilot demand and readiness.
askalpha | executive update | September 2026
Basis: S2–S7, W1–W3
08
INTEGRATION
WHY IT MATTERS
PROPOSED TIMING
DECISION REQUIRED
Databricks
Genie
Reuse analytics capability;
avoid duplicate development.
MVP 1: evaluate one domain.
MVP 2: integrate if qualified.
Sponsor a
comparative pilot.
On-premises
databases
Reach selected data without
a mandatory cloud migration.
MVP 1: select source and access path.
MVP 2: first targeted connector.
Name use case
and source owner.
Collibra
Reuse approved definitions;
reduce manual metadata upkeep.
MVP 1: ownership and metadata contract.
MVP 2: read-only ingestion and refresh.
Assign metadata
and API owners.
A required on-premises source may enter MVP 1 only when the approved pilot cannot proceed without it.
SEQUENCING RULE
Start discovery early; commit to integration only after a bounded business and control test.
Notes: These are three proposed integration workstreams with different roles: Genie provides a candidate analytics route; on-premises connectors extend data access; Collibra provides governed metadata. They are not substitutes for one another. Current SQL support remains unchanged. The three integration scopes are proposed, not active dependencies. Engineering Phase 3 is the integration phase, not executive MVP 3. Provider-native access and approval prerequisites must be verified. No user-permission synchronization is introduced.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W1] Microsoft Learn: Use the Genie Agents API. https://learn.microsoft.com/en-us/azure/databricks/genie-agents/conversation-api . Checked 9 Sep 2026. The API supports embedding conversational analytics; quality still depends on curated context and testing. API authorization and data/warehouse permissions must be confirmed for the chosen enterprise identity pattern.
[W2] Microsoft Learn: Connect to external databases and catalogs. https://learn.microsoft.com/en-us/azure/databricks/query-federation/ . SQL Server: https://learn.microsoft.com/en-us/azure/databricks/query-federation/sql-server . Oracle: https://learn.microsoft.com/en-us/azure/databricks/query-federation/oracle . Checked 9 Sep 2026. External database access is also possible through Databricks federation; the askalpha proposal is platform choice, not exclusive connectivity or guaranteed lower cost.
[W3] Collibra developer documentation: APIs https://developer.collibra.com/api ; Output Module https://developer.collibra.com/api/guides/output-module . Checked 9 Sep 2026. Supported APIs can retrieve assets, attributes and relationships. Availability, populated metadata, credentials, permissions and enterprise approval remain to be confirmed in the relevant environment.

## Slide 9
DATABRICKS GENIE · EVALUATE NOW
askalpha
Evaluate Genie now; adopt only where it proves value.
Potential value: reuse Databricks analytics while preserving the askalpha experience and controls.
askalpha | executive update | September 2026
Basis: S3, S7, W1
09
HIGH STRATEGIC VALUE
MVP 1: ASSESS → MVP 2: CONDITIONAL
Engineering integration: Phase 3
VALUE
Reduce duplicate analytics development.
Keep product-level access and audit.
FIRST TEST
One curated domain and agreed questions.
Compare direct SQL and Genie end to end.
GO / NO-GO GATE
Quality and pre-execution access isolation.
Latency, total cost and support ownership.
askalpha
Access • Semantics • Audit
Selected Genie domain
Candidate analytics provider
Governed data
Approved Databricks data scope
Release gate: prove end-user scope is enforced before Genie executes—not only when results return.
LEADERSHIP ASK
Sponsor one measured comparison; do not make Genie a dependency of the core pilot.
Notes: Proposed, not started or approved: assess Genie on one curated Databricks-resident domain using the same golden questions and authorization scopes as the direct path. The API offers an embedding route, but the vendor capability is not evidence of enterprise deployment or answer quality. A Genie request may execute queries; wrapping the returned answer in an application check is not sufficient. With shared workload identity, an approved restricted domain/object boundary or equivalent pre-execution control must enforce the end user’s permitted entity scope. No continuous user-ACL mirror is introduced. Reject or defer the candidate if the chosen provider cannot satisfy that boundary. Compare accuracy, evidence, response time, query cost, model cost, operations and maintainability before recommending rollout. Timing is MVP 1 assessment, conditional MVP 2 implementation via engineering Phase 3.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W1] Microsoft Learn: Use the Genie Agents API. https://learn.microsoft.com/en-us/azure/databricks/genie-agents/conversation-api . Checked 9 Sep 2026. The API supports embedding conversational analytics; quality still depends on curated context and testing. API authorization and data/warehouse permissions must be confirmed for the chosen enterprise identity pattern.

## Slide 10
KEY FACTOR COMPARISON
askalpha
askalpha vs Genie: compare value beyond model access.
Documented askalpha scope vs. vendor capability. Neither has a measured cost or performance win here.
askalpha | executive update | September 2026
Basis: project evidence + official docs · 9 Sep 2026
10
DECISION FACTOR | askalpha | DATABRICKS GENIE
Delivery & ownership | Accepted SQL pilot; the team owns product expansion and ongoing support. | Packaged analytics; domain curation, testing and operations remain necessary.
Cloud & on-premises | Azure-based today; direct on-premises adapters are planned—not deployed proof. | Cloud-hosted; supported external data via federation. Not a fully offline service.
Frontier models | Approved models can be routed by the app. Access to GPT is not an exclusive advantage. | Partner-powered Chat: Azure OpenAI. Agent mode: Anthropic; versions unverified.
Performance | No representative end-to-end benchmark. Early request/result caching remains planned. | Measure AI + warehouse latency on the same questions; test warm and cold states.
Scale: ~5 TB+ | Planning context—not qualified capacity. Large queries stay on the source platform. | Warehouse scale is available; test burst load, scan cost and query limits.
Semantics & change | Versioned registry, one governed calculation and field-level change protection. | Curated definitions, trusted SQL, benchmarks and version-controlled configuration.
Authorization | App-owned entity scope + source identity. No user-permission synchronization. | Native user catalog controls; a service API route must prove pre-execution isolation.
Economic fit | Custom controls and direct-source choice must justify build and support costs. | Budget paid inference + query compute; measure total cost per accepted answer.
DECISION LENS
Both can use frontier AI. Compare controls, coverage and full forward ownership cost.
Notes: KEY FACTOR COMPARISON — 70/30 NON-PROMOTIONAL REVISION
Purpose: preserve the executive comparison while correcting any implication that Genie lacks frontier models or has permanently free inference. This is a dated evidence comparison, not a deployment verification or a procurement recommendation.
1. DOCUMENTED ASKALPHA FOUNDATION
The accepted historical scope through Phase 2E includes secure bounded read-only SQL, entity permissions, governed metadata and plans, one approved calculation and field dependency/change evidence. Phase 2F.1 implementation/review was reported in the 1 September impact report, with final integration needing re-verification. New source connectors, distributed result caches and advanced formatting are not asserted as deployed. Existing metadata caching is not early answer caching.
2. MODEL ACCESS IS NOT AN EXCLUSIVE DIFFERENTIATOR
The Azure Databricks partner-powered feature table maps Genie Agents Chat to Azure OpenAI and Agent mode to Anthropic on Databricks. This is conditional on the applicable feature settings and availability. It does not identify the exact model version, per-question routing, number of calls or internal token budgets. The GPT-5.2 / Sonnet 4.6 mix on slide 11 is a costing reference, not an observed Genie configuration or a newly approved askalpha deployment. Do not add direct GPT/Claude charges again for the same calls already counted in Genie inference. Separate askalpha-owned calls are incremental.
3. CLOUD AND ON-PREMISES
askalpha is currently Azure-dependent; a data-adapter boundary does not establish multi-cloud hosting or an on-premises product. Direct access to one selected on-premises database remains planned and needs supported workload identity, network, scope and capacity qualification. Databricks federation can access supported external databases. Source, Databricks and network costs may all apply. Neither is a fully offline solution in the compared architecture.
4. PERFORMANCE AND SCALE
No platform is declared faster or cheaper from the 5-TB source size. Compare accepted-answer accuracy and end-to-end p50/p95 under the same data snapshot, question mix and user scope. Separate model work, queue time, cold start, SQL and output formatting. Active sessions are not identical to concurrent running queries. A shared compute budget is a financial assumption, not proof of equal capacity or workload.
5. SEMANTICS AND ACCESS
Semantic governance is not unique to askalpha: Genie offers curation, trusted SQL, benchmarks and versioned configuration. Test actual change behavior and answer-level evidence. Preserve askalpha's application-owned entity authorization and service-identity access without user-ACL mirroring. A Genie integration using a shared identity must prove the permitted scope before execution. Prompt instructions and post-result filtering alone are insufficient controls.
6. ECONOMIC DECISION
Use non-promotional, gross consumption as the comparison basis; credits and negotiated discounts are separate. The cost slide is a model-equivalent estimate with explicit inputs, not a Genie price quote. Both options require data curation, business validation, support, security and governance. Compare future TCO per accepted answer, including remaining delivery work, rather than token price or feature count alone.
SOURCES
Internal: current-state record verified 26 Aug 2026 (file_00000000794881fdbf5e728f1de30ebd); ARCHITECTURE_DELTA_IMPACT_REPORT.md dated 1 Sep 2026 (file_00000000d9c081f6a266f8bdbf5b513f); owner architecture and 70/30 workload decisions in this conversation.
Public primary sources, checked 9 Sep 2026:
- https://learn.microsoft.com/en-us/azure/databricks/databricks-ai/partner-powered
- https://learn.microsoft.com/en-us/azure/databricks/genie-agents/concepts
- https://learn.microsoft.com/en-us/azure/databricks/genie-agents/conversation-api
- https://learn.microsoft.com/en-us/azure/databricks/genie-agents/best-practices
- https://learn.microsoft.com/en-us/azure/databricks/query-federation/
- https://learn.microsoft.com/en-us/azure/databricks/compute/sql-warehouse/warehouse-types
- https://learn.microsoft.com/en-us/azure/databricks/genie/monitor-cost

## Slide 11
COST COMPARISON · NON-PROMOTIONAL 70/30 SCENARIO
askalpha
Budget paid AI—not promotional zero usage.
Gross monthly model-equivalent estimate—not metered Genie charges, a 2027 supplier quote or full TCO.
askalpha | executive update | September 2026
Basis: 70/30 assumptions + public rates · 9 Sep 2026
11
10,000 questions/month | 70% simple / 30% complex | No promotion, free credits or cache savings
MONTHLY COST / USD | askalpha direct | Genie native UI | askalpha + Genie service identity
Query compute (shared assumed budget) | $1,760.00 | $1,760.00 | $1,760.00
App + control services (assumed budget) | $600.00 | $0.00** | $600.00
AI budget (model-equivalent*) | $883.30 | $883.30 G1* | $883.30 G2*
OPERATING SUBTOTAL | $3,243.30 | $2,643.30 | $3,243.30
MODEL-REFERENCE BUILD-UP
70% SIMPLE · GPT-5.2
7,000 × $0.0385 = $269.50
30% COMPLEX · SONNET 4.6
3,000 × $0.2046 = $613.80
$883.30 / month
Includes 10% retry/repair allowance.
Equal usage for G1/G2 is assumed.
AI sensitivity: $883–$2,316/month, not a ceiling. Optional extra hybrid GPT call: +$115.50/month.
* G1/G2 are budget proxies, not Genie tariffs. Compute: 220h × $8; app: $600. These budgets and capacity are unverified.
** No custom app in native UI. Excludes people, delivery, source/storage, network and security/DR. Method in Notes.
INVESTMENT RULE
Replace the proxy with metered, non-promotional cost per correct, accepted answer.
Notes: CALCULATION METHODOLOGY — NON-PROMOTIONAL 70/30 MODEL-EQUIVALENT ESTIMATE
REVISION AND PURPOSE
This slide replaces the earlier promotional-zero Genie comparison and the $385 single-profile model estimate. It uses the owner's 70% simple / 30% complex workload assumption. All figures are USD/month. No temporary promotion, free allowance, negotiated discount, batch discount, prompt-cache saving or early-result-cache saving is included. Current public rates are reference inputs, not guaranteed prices after January 2027. This is NOT an actual Genie tariff/invoice, an Azure quote, qualified production capacity, or full total cost of ownership. The earlier Excel workbook and cost slide are superseded for this scenario; the workbook itself has not been edited in this slide-only revision.
1. BASE WORKLOAD
Total business questions/month: 10,000.
Simple questions: 10,000 x 70% = 7,000.
Complex questions: 10,000 x 30% = 3,000.
The percentage split is an owner planning assumption, not a measured distribution. A business question can involve multiple model and query calls.
5 TB is source-data planning context only. It is neither cache size nor a multiplier that determines model cost or warehouse size. Thirty peak active users are not thirty monthly active users or thirty simultaneous queries.
2. STANDARD MODEL REFERENCE PRICES
GPT-5.2: $1.75 per million input tokens; $14 per million output tokens.
Claude Sonnet 4.6: $3 per million input tokens; $15 per million output tokens.
Claude Opus 4.6, sensitivity only: $5 per million input; $25 per million output.
Rates were checked in OpenAI and Anthropic official public documentation on 9 September 2026. They are direct/public standard API references, not the organization's Azure deployment rates, Databricks Genie invoice rates, or a forecast price for 2027. No new model or provider deployment is authorized by the estimate. Regional data-residency premiums, tool fees and contract terms can change the actual charge and must be added where applicable.
3. CONSUMPTION ASSUMPTIONS
Simple: GPT-5.2 reference; total 8,000 input and 1,500 billed output/reasoning tokens per question before retries.
Complex: Sonnet 4.6 reference; total 32,000 input and 6,000 billed output/reasoning tokens per question before retries.
Complex usage is assumed to be four times the simple token budget. It is NOT a measured Genie multiplier. Totals cover the whole successful answer workflow, including prompts, history, tool-result context and billable reasoning, not just the visible final answer. Do not multiply by the number of internal calls again when those calls are already included.
Retry/repair allowance: 10% additional proportional token usage on both categories. This is an assumption; replace it with all actual billed calls. Additional non-token tool charges are not included.
4. SIMPLE QUESTION CALCULATION
Input = 8,000 x $1.75 / 1,000,000 = $0.014.
Output = 1,500 x $14 / 1,000,000 = $0.021.
Per question with allowance = ($0.014 + $0.021) x 1.10 = $0.0385.
Monthly simple AI = 7,000 x $0.0385 = $269.50.
Monthly simple tokens including allowance: 61.6 million input and 11.55 million billed output.
5. COMPLEX QUESTION CALCULATION
Input = 32,000 x $3 / 1,000,000 = $0.096.
Output = 6,000 x $15 / 1,000,000 = $0.090.
Per question with allowance = ($0.096 + $0.090) x 1.10 = $0.2046.
Monthly complex AI = 3,000 x $0.2046 = $613.80.
Monthly complex tokens including allowance: 105.6 million input and 19.8 million billed output.
6. TOTAL AI BUDGET AND G1/G2
AI = $269.50 + $613.80 = $883.30/month.
Average = $883.30 / 10,000 = $0.08833 per business question.
The 30% complex category generates about 69.5% of this model-reference cost.
G1* = $883.30: gross model-equivalent proxy for Genie native-user AI.
G2* = $883.30: gross model-equivalent proxy for Genie service-identity AI.
The equality is imposed ONLY to compare the same assumed mix and consumption before all credits. It does not establish equal real usage, model versions, tokenizers, execution modes or answer quality. The same $883.30 is applied to askalpha for fairness instead of retaining the lower, obsolete single-profile $385 estimate. Real G1 and G2 must be metered separately and can differ materially.
The partner-powered documentation identifies Azure OpenAI for Genie Agents Chat mode and Anthropic on Databricks for Agent mode. It does not reveal exact versions or consumption. Do not state that Genie routes precisely 70% to GPT-5.2 and 30% to Sonnet 4.6; that is an analytical reference, not an observed Genie design.
Do not add separate GPT/Claude prices again for the same inference already included in a metered Genie charge. An independent model call made by askalpha is a separate cost.
7. COMPUTE AND APPLICATION BUDGETS
Compute = 22 business days x 10 hours/day x $8/billed cluster-hour = $1,760/month.
$8 is an assumed all-in serving-compute budget, NOT a published SQL Warehouse size/region/SKU rate. Count all billed clusters, startup, idle and autoscale hours. The same compute envelope is held constant for arithmetic; it does not prove that 220 cluster-hours can meet the 70/30 workload on 5 TB. Complex analysis can issue additional queries and increase compute.
askalpha app/control services = $250 UI/API hosting + $250 retrieval/search + $100 registry/audit = $600/month. These are unverified budgets, not production HA/DR/WAF/SIEM specifications.
Native Genie UI has no bespoke askalpha application in this scenario, so its custom-app budget is $0. This does not mean domain curation, licensing, governance or support is free.
Hybrid assumes the same $600 app budget and no duplicate askalpha-owned LLM work in the base case.
8. MONTHLY TOTALS
askalpha direct = $1,760 + $600 + $883.30 = $3,243.30.
Genie native UI = $1,760 + $0 + G1* = $2,643.30.
askalpha + Genie service identity = $1,760 + $600 + G2* = $3,243.30.
The $600 difference for native Genie follows solely from the assumed custom-app budget, not free AI or evidence of lower full TCO.
Per-question operating subtotals: askalpha $0.32433; native Genie proxy $0.26433; hybrid proxy $0.32433. These are per submitted question, not quality-adjusted accepted-answer costs.
Static 12-month run rates at unchanged prices, usage and capacity: askalpha/hybrid $38,919.60; Genie UI proxy $31,719.60. These are not a dated annual budget, contractual quote or forecast of post-promotion prices.
9. OPTIONAL EXTRA HYBRID MODEL CALL
Assume askalpha makes an independent GPT-5.2 call on every question with 2,000 input and 500 billed output tokens, plus the same 10% allowance.
E/question = [(2,000 x $1.75 + 500 x $14) / 1,000,000] x 1.10 = $0.01155.
E/month = 10,000 x $0.01155 = $115.50.
Hybrid with E = $3,243.30 + $115.50 = $3,358.80/month.
This is separate app-owned work. Its inclusion does not double-charge Genie-internal model calls. Change the call count and token budgets to match actual architecture.
10. COMPLEXITY / MODEL SENSITIVITY
Simple category stays at $269.50 in all cases. Only the complex category changes; retry allowance stays 10%.
A. Sonnet 4.6, 32,000 input / 6,000 output: AI $883.30; native Genie proxy total $2,643.30; hybrid proxy $3,243.30.
B. Sonnet 4.6, 64,000 / 12,000: AI $1,497.10; native Genie proxy $3,257.10; hybrid proxy $3,857.10.
C. Opus 4.6, 32,000 / 6,000: AI $1,292.50; native Genie proxy $3,052.50; hybrid proxy $3,652.50.
D. Opus 4.6, 64,000 / 12,000: AI $2,315.50; native Genie proxy $4,075.50; hybrid proxy $4,675.50.
Formula in each case: 7,000 x simple_cost + 3,000 x [(complex_input x input_rate + complex_output x output_rate)/1,000,000] x 1.10.
The displayed $883-$2,316 band is rounded sensitivity, NOT a confidence interval, vendor price range or maximum. Longer context, other models, extra tools, retries, queries or provider charges can exceed it. Compute has been held unchanged and must be re-sized if measured load increases.
11. REPLACE THE PROXY WITH REAL GENIE BILLING
Use the relevant Genie Agents usage and identity filters in system.billing.usage and the matching SKU, currency, cloud/region and validity period in system.billing.list_prices; reconcile corrections/retractions and the negotiated invoice. Do not use a SQL DBU price for Genie inference DBUs. Meter query compute separately.
Official documentation checked 9 Sep 2026 states that human Genie Agents/One usage is temporarily free through 31 Jan 2027; service principals are excluded. A 25% billed-usage promotion is embedded in billed DBU metering. The free 150-DBU/user monthly allowance is a separate entitlement, not a service-principal entitlement. No benefit from either is included in the slide.
For billed inference records already discounted by 25%, divide that discounted inference-only amount by 0.75 to form an unchanged-list-price, unchanged-usage non-promotional reference. Do not divide compute or unrelated service costs by 0.75.
Raw free-usage records are metered at full consumption. Price those raw quantities at the applicable paid SKU rate without applying the 25% adjustment again. If instead using the documentation's estimated_list_cost query result, note that that estimate already includes the promotional 25%; normalize it only once. Credit eligibility and any credit already used by another Genie product must be evaluated per user, not by multiplying peak active users by a generic credit amount.
After-promotion rates are not guaranteed by current documentation. Budget at current gross references, then refresh rates and contract terms for the actual billing period.
12. EXCLUSIONS AND APPROVAL BOUNDARY
All three operating subtotals exclude remaining engineering, connector implementation, data/semantic preparation, migration, source storage/licenses, private networking/egress, security/compliance/MRM, business testing, HA/backup/DR, audit retention, support and enterprise overhead. No source is assumed free merely because it already exists. No model or compute capacity has been benchmarked here.
Full forward TCO = remaining one-time delivery + future runtime + semantic curation + validation/governance + people/operations + network/security/recovery. Do not charge sunk historical work again. An illustrative additional 40 support hours at $100/hour equals $4,000/month and can exceed the model-cost difference; this is not an actual staffing rate.
Judge cost per correct and accepted answer at equivalent access scope and service quality. A bounded comparative pilot should record real model/DBU consumption, query counts/hours, warm/cold p50/p95, quality, denied-scope behavior and support effort before procurement or rollout decisions.
SOURCES — PUBLIC PRIMARY SOURCES CHECKED 9 SEPTEMBER 2026
[W1] GPT-5.2 reference model pricing: https://developers.openai.com/api/docs/models/gpt-5.2
[W2] Claude standard pricing, Sonnet 4.6 and Opus 4.6: https://platform.claude.com/docs/en/about-claude/pricing
[W3] Genie cost and metering: https://learn.microsoft.com/en-us/azure/databricks/genie/monitor-cost
[W4] Genie billing FAQ and discount normalization: https://learn.microsoft.com/en-us/azure/databricks/genie/genie-cost-budgets-faq
[W5] Azure partner-powered feature table: https://learn.microsoft.com/en-us/azure/databricks/databricks-ai/partner-powered
[W6] Genie pricing / query-compute boundary: https://www.databricks.com/product/pricing/genie
[U1] Owner request: 70% simple / 30% complex questions; compare paid non-promotional usage. The 10,000 questions, 4x complex token budget, 10% allowance and compute/app budgets are scenario inputs, not measurements.
[P1] ARCHITECTURE_DELTA_IMPACT_REPORT.md, 1 Sep 2026: planned early/result caches and provider expansions are not credited as deployed cost savings.

## Slide 12
ON-PREMISES DATA · BUSINESS-LED
askalpha
Prove independence with one on-premises use case.
Potential value: reach approved data in place without forcing every request through Databricks.
askalpha | executive update | September 2026
Basis: S2, S5, S7, W2
12
HIGH VALUE · DEMAND-LED
MVP 1: DISCOVER → MVP 2: FIRST SOURCE
A TARGETED DIRECT PATH
askalpha
User scope + governed question
Source adapter
Approved network + service identity
One on-premises source
Read-only views • bounded queries
Illustrative target; not a confirmed live connection.
01
Select the first source
One SQL Server or Oracle use case—not all databases.
02
Approve access and workload
Validate network, service identity and source capacity.
03
Prove the operating model
Bound queries; test peak load, cost and safe failure.
Existing SQL support does not prove on-premises connectivity. Source and network costs still apply.
LEADERSHIP ASK
Choose the first source and accountable owner; bring it forward only if the pilot requires it.
Notes: Proposed sequence: confirm the business question and one required on-premises database during MVP 1; deliver a source-specific read-only adapter and tested connectivity in engineering Phase 3 / MVP 2. A single essential source may be moved into MVP 1 by explicit scope and readiness approval, not by making every on-premises platform a prerequisite. Managed Identity is preferred where actually supported; do not assume all on-premises SQL Server or Oracle systems accept it. IAM must approve the source-appropriate workload identity, secret handling where needed, network and server configuration. Service identity only defines the application envelope; askalpha continues to enforce end-user entity scope before execution. Execute heavy analytical work on an approved source/read replica and return bounded results; assess source workload impact, licenses, network and operations as costs. Databricks federation also supports external SQL Server and Oracle access. The differentiator proposed here is the option of direct execution without a mandatory Databricks intermediary, not a claim that Genie/Databricks cannot access external data or that this route is free.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W2] Microsoft Learn: Connect to external databases and catalogs. https://learn.microsoft.com/en-us/azure/databricks/query-federation/ . SQL Server: https://learn.microsoft.com/en-us/azure/databricks/query-federation/sql-server . Oracle: https://learn.microsoft.com/en-us/azure/databricks/query-federation/oracle . Checked 9 Sep 2026. External database access is also possible through Databricks federation; the askalpha proposal is platform choice, not exclusive connectivity or guaranteed lower cost.

## Slide 13
COLLIBRA · GOVERNED METADATA REUSE
askalpha
Reuse definitions without creating a competing catalog.
Potential value: reuse approved meaning, ownership and classifications as the data estate grows.
askalpha | executive update | September 2026
Basis: S3, S4, S7, W3
13
HIGH GOVERNANCE VALUE
MVP 1: CONTRACT → MVP 2: READ-ONLY INTEGRATION
Collibra
Approved metadata
and named owners
Validate & map
Check evidence;
publish under review
Semantic Registry
Versioned runtime
semantic snapshot
Plans & templates
Reference approved
IDs and versions
Read-only metadata intake; not analytical-data movement and not a per-question API dependency.
AGREE IN MVP 1
Owners and approved scope
Assign definition owners;
agree mapping and freshness.
DELIVER IN MVP 2
Read-only metadata intake
Validate and publish snapshots;
monitor refresh failures.
KEEP OWNERSHIP CLEAR
One runtime semantic contract
Preserve source and version;
templates only reference them.
LEADERSHIP ASK
Confirm metadata and API owners. Metadata integration is not user-permission synchronization.
Notes: Proposed Collibra boundary: the enterprise owner decides which approved definitions and governance attributes originate in Collibra or another system of record. askalpha publishes a validated, versioned canonical runtime snapshot; it must not become a competing authoring authority for imported definitions. Templates reference semantic IDs and versions, not re-encoded KPIs. The Collibra API/Output Module can retrieve relevant assets, attributes and relationships. Actual enterprise metadata population, API access, authentication, approval and freshness remain to be verified. Contract and ownership work can be included in Phase 2F.3 during MVP 1. Read-only adapter, refresh and operational integration are separate Phase 3 / proposed MVP 2 work; avoid expanding the Phase 2F.1 evaluator. Start with one domain and scheduled/controlled refresh rather than a per-question catalog call. Preserve provenance, reject conflicting required evidence, and define stale/unavailable behavior. This is governance metadata intake, not an ACL synchronization engine, and metadata never grants access.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W3] Collibra developer documentation: APIs https://developer.collibra.com/api ; Output Module https://developer.collibra.com/api/guides/output-module . Checked 9 Sep 2026. Supported APIs can retrieve assets, attributes and relationships. Availability, populated metadata, credentials, permissions and enterprise approval remain to be confirmed in the relevant environment.

## Slide 14
PILOT SUCCESS MEASURES
askalpha
Prove business and integration value before wider rollout.
Use the same approved questions and access scope for comparative tests.
askalpha | executive update | September 2026
Basis: S2, S3, S5–S7
14
FOCUSED PILOT
Focused scope.
Measure value.
Business sponsor
Selected data products
Approved test questions
Baseline and review date
Business impact
Time to a trusted answer and reporting effort
compared with the existing process.
Answer quality
Agreement with approved results; preserve
values, dates, sources and warnings.
Access & privacy
No unauthorized disclosure in the agreed tests;
use only approved model payloads.
Operational fit
Response time, freshness, source impact and total cost
for each candidate path under representative peak use.
PILOT EXIT
Expand, adjust or pause based on evidence—not on feature count alone.
Notes: REVISION: Add integration-specific measurement to the pilot scorecard. Compare Genie and direct execution only on equivalent questions, data and permitted scope. For on-premises, include source workload and network impact. For Collibra, measure metadata completeness for the chosen scope, freshness and manual upkeep avoided. Do not claim measured benefits until baselines and tests exist.
PRIOR SLIDE CONTEXT (retained where not superseded)
All measures on this slide are recommendations and not achieved outcomes. No measured productivity gain, reporting reduction, adoption or ROI is available in the reviewed evidence. Peak concurrency is to be agreed for aggregate scope; previous use-case estimates must not be presented as validated enterprise capacity. A pilot acceptance test is not a universal guarantee of security or reliability. Existing regulated/scheduled reports continue unless their owners approve rationalization. The pilot complements those reporting channels rather than committing to replacing them.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S2] Phase journey and manager summary, updated 26 Aug 2026. ChatGPT Library file ID file_00000000e57881fda2f0c1cc493a8779. Management roadmap and feature map, updated 26 Aug 2026: file_00000000212881fd8df615c438684075.
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S5] Architecture and roadmap update, updated 26 Aug 2026: file_00000000a02081fd918c3632e0a5a902. Assumption and decision log: file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution and bounded results; scale qualification remains later work.
[S6] Owner-provided conversation and roadmap photographs. Preserves three delivery milestones: Foundation & Trust; Scale & Efficiency; Advanced Visualization. Latest owner direction: application-owned entity authorization with Managed Identity source access and no user-ACL synchronization; early and post-plan caching; Semantic Registry business authority; deterministic output routing; Genie future evaluation. Two-week demos are a proposed cadence, not committed release dates.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 15
DECISIONS REQUIRED
askalpha
Six decisions turn integration options into a delivery plan.
Confirm the priorities and accountable functions; implementation remains separately gated.
askalpha | executive update | September 2026
Basis: S3–S7 · proposed decisions
15
DECISION
LEADERSHIP ACTION
ACCOUNTABLE FUNCTIONS
01
Pilot focus
& capacity
Approve pilot scope and bounded integration discovery;
confirm capacity and success measures.
Business sponsor
& Product
02
Genie
evaluation
Choose one domain and agreed comparison criteria;
sponsor the assessment before any rollout decision.
Product
& Architecture
03
On-premises
priority
Name the first use case and source owner;
confirm the access path and workload budget.
Data owners
& Platform
04
Collibra
& semantics
Name definition and API owners; approve the
read-only metadata contract and refresh expectations.
Data Governance
& Platform
05
Controls
& privacy
Agree approval/change policies and permitted AI use;
keep result-formatting AI off until approved.
Governance / Product
& Privacy / Security
06
Operations
& release
Set service and cost goals, acceptance evidence
and the pilot go/no-go authority.
Architecture
& Operations
RECOMMENDED ASK
Endorse the sequence and assign owners; commit delivery dates only after readiness is confirmed.
Notes: The new rows explicitly request decisions for Genie, on-premises connectivity and Collibra, not just general platform approval. These are accountable-function proposals; no named owner is assigned by this deck. Core business approval/renewal/change policy, AI privacy, operational targets and release evidence remain required. Do not interpret the six decisions as blanket production approval, an open-ended connector program or a funding commitment. No funding authorization or fixed date is implied; the comparison slide provides an explicitly assumed operating-cost scenario, not an approved budget. Entity-level application authorization and service-identity access remain the working MVP model with no user-ACL synchronization.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 16
APPENDIX · DELIVERY CONFIDENCE
askalpha
Capability status: what is delivered versus still ahead.
Architecture decisions are not evidence of production activation.
askalpha | executive update | September 2026
Evidence: S1–S5
16
DOCUMENTED DELIVERY
Accepted foundation through 2E
Secure SQL access; governed registry and plans; one approved calculation;
field-change protection; provider-neutral source boundary.
REPORTED IMPLEMENTATION
Lifecycle classification (2F.1)
Implementation and independent review are reported. Current merge /
activation state has not been reverified for this presentation.
WORKING DESIGN DECISIONS
Clear ownership and safe extensibility
Registry owns business meaning; application owns user scope; no ACL sync;
fixed formatting rules; early plus result-cache design.
PLANNED / CONDITIONAL
Broader operational and user capabilities
Certified catalog/templates; caching; Genie assessment, on-premises and Collibra
integrations; self-service and exports. Runtime rollout remains approval-gated.
IMPORTANT DISTINCTION
Metadata snapshot caching exists; request/result-cache rollout is still planned.
Notes: REVISION: Planned integration opportunities are now timed, not reclassified as implemented. Genie remains a candidate and may fail its evaluation. On-premises access and Collibra API readiness are not established by the current SQL foundation. Source/version metadata provenance complements the runtime Registry authority; no competing definition store is proposed.
PRIOR SLIDE CONTEXT (retained where not superseded)
This status matrix reconciles the historical 26 August current-state record with the 1 September impact report. It does not assign a percentage completion or infer any deployment. 2F.1 evidence concerns a classification-only evaluator, default OFF; this does not mean approved operational policy is active. The design decisions are owner-level working program direction, not blanket enterprise approval. Treat every new provider and optional AI result boundary as separately qualified.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S1] Authoritative current-state record, updated 26 Aug 2026. ChatGPT Library file ID file_00000000794881fdbf5e728f1de30ebd. Foundation through 2E; one pilot dataset/recipe; 199 governed fields; bounded evidence and successful workflows.
[S2] Phase journey and manager summary, updated 26 Aug 2026. ChatGPT Library file ID file_00000000e57881fda2f0c1cc493a8779. Management roadmap and feature map, updated 26 Aug 2026: file_00000000212881fd8df615c438684075.
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. ChatGPT Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Lifecycle, approval policy, certified meaning, templates, evidence-gated relationships and acceptance conditions.
[S5] Architecture and roadmap update, updated 26 Aug 2026: file_00000000a02081fd918c3632e0a5a902. Assumption and decision log: file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution and bounded results; scale qualification remains later work.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S1] Authoritative current-state record, updated 26 Aug 2026. Library file ID file_00000000794881fdbf5e728f1de30ebd. Accepted foundation through 2E; one governed pilot dataset and calculation; 199 evidenced fields. Historical delivery evidence, not a live production check.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 17
APPENDIX · PHASE CROSSWALK AND EVIDENCE
askalpha
Executive milestones are not engineering phase numbers.
Proposed packaging of the existing roadmap—not renumbering or new delivery evidence.
askalpha | executive update | September 2026
Basis: S1–S7, W1–W3
17
EXECUTIVE MILESTONE
ENGINEERING ALIGNMENT
MVP 1
Foundation & Trust
Accepted foundation through 2E; 2F trust/lifecycle/templates and 2G controlled publishing. Integration discovery may run in parallel.
MVP 2
Enterprise Integration
& Efficiency
Phase 3: selected providers, Genie and metadata integration. Phases 4–7: safety, evaluation, performance and self-service.
MVP 3
Advanced Visualization
Phase 8: richer visualization, reports, downloads, exports and approved experience integrations.
Collibra contract: Phase 2F.3. Provider implementation: Phase 3.
An essential on-premises source may be brought forward by explicit pilot scope approval.
EVIDENCE BOUNDARY
Foundation record: 26 Aug 2026.
Impact report: 1 Sep 2026.
2F.1 final integration has not
been live-reverified here.
Vendor docs checked 9 Sep 2026;
enterprise readiness is not proven.
5 TB+ is planning context.
Dates, savings and scale are not promised.
REFERENCE DETAIL
Speaker notes retain source references, vendor links and the qualifications behind each slide.
Notes: Crosswalk is an executive presentation recommendation, not an approved technical renumbering. Existing engineering roadmap is preserved. Phase 2F.3 defines certified semantic contracts; integrating live Collibra and other provider APIs is separate Phase 3 work. Phase 3 also contains Databricks/provider work and the Genie coexistence boundary. Broader safety/evaluation/performance/self-service phases contribute to executive MVP 2; engineering Phase 8 supports executive MVP 3. Preparatory discovery does not require waiting for the end of MVP 1, but runtime activation still requires the relevant gates. Source evidence remains historical through accepted 2E with a 1 September 2F.1 review. No repository, deployment, service-access or environment check was conducted for this presentation. Vendor docs only support external feature feasibility. Approximately 5 TB or more is a planning context, not a demonstrated capacity.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S1] Authoritative current-state record, updated 26 Aug 2026. Library file ID file_00000000794881fdbf5e728f1de30ebd. Accepted foundation through 2E; one governed pilot dataset and calculation; 199 evidenced fields. Historical delivery evidence, not a live production check.
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S6] Owner-supplied conversation and previous roadmap photographs. Three executive milestones and green/white design direction. Application-owned entity authorization; service-identity source access; no mirrored user ACLs; governed semantics, templates and cache design. Photos are visual/reference material, not evidence of delivery or measured ROI.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W1] Microsoft Learn: Use the Genie Agents API. https://learn.microsoft.com/en-us/azure/databricks/genie-agents/conversation-api . Checked 9 Sep 2026. The API supports embedding conversational analytics; quality still depends on curated context and testing. API authorization and data/warehouse permissions must be confirmed for the chosen enterprise identity pattern.
[W2] Microsoft Learn: Connect to external databases and catalogs. https://learn.microsoft.com/en-us/azure/databricks/query-federation/ . SQL Server: https://learn.microsoft.com/en-us/azure/databricks/query-federation/sql-server . Oracle: https://learn.microsoft.com/en-us/azure/databricks/query-federation/oracle . Checked 9 Sep 2026. External database access is also possible through Databricks federation; the askalpha proposal is platform choice, not exclusive connectivity or guaranteed lower cost.
[W3] Collibra developer documentation: APIs https://developer.collibra.com/api ; Output Module https://developer.collibra.com/api/guides/output-module . Checked 9 Sep 2026. Supported APIs can retrieve assets, attributes and relationships. Availability, populated metadata, credentials, permissions and enterprise approval remain to be confirmed in the relevant environment.
COST REVISION: Slide 11 supersedes the older promotional-zero and $385 examples. It now uses 10,000 questions/month, a 70/30 simple/complex split, paid model-equivalent AI of $883.30 before all credits, and the same unverified compute/app budgets. See slide 11 Notes for formulas, sensitivity and the actual Genie-metering replacement method. No 2027 price guarantee or full-TCO claim is made.