## Slide 1
askalpha
EXECUTIVE DELIVERY UPDATE
From working answers
to governed scale
Progress delivered. Strategic integrations. Decisions required.
DELIVERED
A governed SQL
foundation
NEXT
A controlled
business pilot
DECIDE
Priorities, ownership
and readiness
Foundation & Trust → Enterprise Integration & Efficiency → Advanced Visualization
September 2026
Notes: REVISION: MVP 2 now includes targeted enterprise integrations as well as efficiency. Genie, on-premises connectivity and Collibra are proposed workstreams; none is newly claimed as implemented.
PRIOR SLIDE CONTEXT (retained where not superseded)
Leadership update. This uses the documented accepted foundation through 2E, the 1 September architecture delta and owner decisions. Existing business-question capability is a bounded working proof of concept. The three-card summary does not imply that the governed business pilot or production rollout has already been approved. No financial return or launch date is asserted.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S1] Authoritative current-state record, updated 26 Aug 2026. ChatGPT Library file ID file_00000000794881fdbf5e728f1de30ebd. Foundation through 2E; one pilot dataset/recipe; 199 governed fields; bounded evidence and successful workflows.
[S2] Phase journey and manager summary, updated 26 Aug 2026. ChatGPT Library file ID file_00000000e57881fda2f0c1cc493a8779. Management roadmap and feature map, updated 26 Aug 2026: file_00000000212881fd8df615c438684075.
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S6] Owner-provided conversation and roadmap photographs. Preserves three delivery milestones: Foundation & Trust; Scale & Efficiency; Advanced Visualization. Latest owner direction: application-owned entity authorization with Managed Identity source access and no user-ACL synchronization; early and post-plan caching; Semantic Registry business authority; deterministic output routing; Genie future evaluation. Two-week demos are a proposed cadence, not committed release dates.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S1] Authoritative current-state record, updated 26 Aug 2026. Library file ID file_00000000794881fdbf5e728f1de30ebd. Accepted foundation through 2E; one governed pilot dataset and calculation; 199 evidenced fields. Historical delivery evidence, not a live production check.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 2
LEADERSHIP BRIEF
askalpha
Deliver the trust milestone; prepare targeted integrations.
Keep core delivery moving while clarifying the next sources, services and owners.
askalpha | executive update | September 2026
Evidence: S1–S3, S7
02
COMPLETED FOUNDATION
Safer, repeatable
answers
Secure, read-only access
Versioned metadata and validated analytical plans
One governed calculation with field-change protection
IN DELIVERY / NEXT
Governed business
readiness
Approval and change policies
Certified definitions and consistent output templates
Controlled pilot and integration discovery
LEADERSHIP ASK
Close the decisions
that unlock delivery
Pilot scope and accountable owners
Genie, on-premises and Collibra priorities
Value, privacy and operating gates
RECOMMENDATION
Complete the core pilot; qualify integrations before committing to wider rollout.
Notes: REVISION: Integration discovery can proceed alongside MVP 1; runtime integrations remain gated. The proposed workstreams do not replace approval, privacy or production-readiness obligations.
PRIOR SLIDE CONTEXT (retained where not superseded)
The completed column refers to engineering-delivered capability in the governed pilot, not enterprise-wide certification. The next column combines reported in-progress lifecycle work and later planned governance/templates/pilot work. The leadership asks are recommendations, not already approved funding or ownership.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S1] Authoritative current-state record, updated 26 Aug 2026. ChatGPT Library file ID file_00000000794881fdbf5e728f1de30ebd. Foundation through 2E; one pilot dataset/recipe; 199 governed fields; bounded evidence and successful workflows.
[S2] Phase journey and manager summary, updated 26 Aug 2026. ChatGPT Library file ID file_00000000e57881fda2f0c1cc493a8779. Management roadmap and feature map, updated 26 Aug 2026: file_00000000212881fd8df615c438684075.
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S6] Owner-provided conversation and roadmap photographs. Preserves three delivery milestones: Foundation & Trust; Scale & Efficiency; Advanced Visualization. Latest owner direction: application-owned entity authorization with Managed Identity source access and no user-ACL synchronization; early and post-plan caching; Semantic Registry business authority; deterministic output routing; Genie future evaluation. Two-week demos are a proposed cadence, not committed release dates.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S1] Authoritative current-state record, updated 26 Aug 2026. Library file ID file_00000000794881fdbf5e728f1de30ebd. Accepted foundation through 2E; one governed pilot dataset and calculation; 199 evidenced fields. Historical delivery evidence, not a live production check.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 3
DELIVERED FOUNDATION
askalpha
Completed work makes the pilot safer and repeatable.
Documented delivery through Phase 2E; verification recorded on 26 August 2026.
askalpha | executive update | September 2026
Evidence: S1, S2, S5
03
CAPABILITY
WHAT HAS BEEN DELIVERED
WHY IT MATTERS
Secure access
Authenticated users, entity permissions
and bounded read-only queries.
Constrains access and
protects source data.
Governed planning
Versioned metadata and validation
of selected data and fields.
Provides a reviewable basis
for the answer.
Repeatable logic
One approved calculation pilot
using governed dependencies.
Reduces improvisation in
important business logic.
Change protection
Checks for missing or materially
changed required field evidence.
Stops affected answers rather
than silently using invalid inputs.
Platform flexibility
A source-adapter boundary around
the current SQL execution path.
Preserves the core when
approved sources are added.
1
governed pilot dataset
1
approved calculation
199
evidenced field definitions
SCOPE MATTERS
These are accepted pilot capabilities—not a claim of enterprise production rollout.
Notes: REVISION: No additional delivered integration or production capability is asserted. Existing SQL execution support is not evidence of a working on-premises deployment.
PRIOR SLIDE CONTEXT (retained where not superseded)
Source S1 records one governed pilot dataset, one approved recipe and 199 strictly evidenced governed fields. These are not enterprise-wide coverage or 199 certified metrics. The documented accepted provider-neutral DataSourceAdapter boundary does not mean Databricks or other source integrations are live. Existing metadata-snapshot caching is not distributed result caching. No current repository state is asserted.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S1] Authoritative current-state record, updated 26 Aug 2026. ChatGPT Library file ID file_00000000794881fdbf5e728f1de30ebd. Foundation through 2E; one pilot dataset/recipe; 199 governed fields; bounded evidence and successful workflows.
[S2] Phase journey and manager summary, updated 26 Aug 2026. ChatGPT Library file ID file_00000000e57881fda2f0c1cc493a8779. Management roadmap and feature map, updated 26 Aug 2026: file_00000000212881fd8df615c438684075.
[S5] Architecture and roadmap update, updated 26 Aug 2026: file_00000000a02081fd918c3632e0a5a902. Assumption and decision log: file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution and bounded results; scale qualification remains later work.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S1] Authoritative current-state record, updated 26 Aug 2026. Library file ID file_00000000794881fdbf5e728f1de30ebd. Accepted foundation through 2E; one governed pilot dataset and calculation; 199 evidenced fields. Historical delivery evidence, not a live production check.
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 4
CURRENT DELIVERY FOCUS
askalpha
Make governed answers operationally manageable.
Extend the accepted foundation without restarting completed work.
askalpha | executive update | September 2026
Evidence: S3, S4
04
LIFECYCLE CLASSIFICATION
Implementation and independent-review evidence reported; final integration status to confirm.
VALID
NEEDS REVIEW
BROKEN
NOT APPROVED
01
Approval & renewal
Name accountable approvers.
Define renewal and change rules.
02
Certified meaning
Agree metric ownership and
Collibra metadata boundaries.
03
Consistent outputs
Use versioned templates and
fixed formatting rules.
DESIGN RULE
Templates reference approved definitions; presentation must not change business meaning.
Notes: REVISION: Collibra source-of-record and import contracts should be considered during Phase 2F.3. The runtime Semantic Registry remains the canonical published semantic snapshot. No new Collibra API or network work belongs in the pure Phase 2F.1 evaluator. Existing 2F.1 status remains reported implementation/review with final integration requiring verification.
PRIOR SLIDE CONTEXT (retained where not superseded)
The 1 September impact report supersedes older statements that all Phase 2F implementation was not started. It reports 2F.1 implemented and independently reviewed, but merge acceptance remains REVERIFY_REQUIRED. Its lifecycle classifier is default-OFF, classification-only and does not itself activate a production execution policy. The cards show next work (2F.2, 2F.3 and 2F.4), not delivery already achieved. Warn versus block for resolvable governed change is an owner decision; missing authorization and invalid required evidence must still fail closed.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. ChatGPT Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Lifecycle, approval policy, certified meaning, templates, evidence-gated relationships and acceptance conditions.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W3] Collibra developer documentation: APIs https://developer.collibra.com/api ; Output Module https://developer.collibra.com/api/guides/output-module . Checked 9 Sep 2026. Supported APIs can retrieve assets, attributes and relationships. Availability, populated metadata, credentials, permissions and enterprise approval remain to be confirmed in the relevant environment.

## Slide 5
ROADMAP AT A GLANCE
askalpha
Three milestones, with enterprise integration made explicit.
MVP 2 expands beyond efficiency; discovery can start alongside the trust milestone.
askalpha | executive update | September 2026
Basis: S2–S7 · proposed sequencing
05
NOW · IN DELIVERY
MVP 1
Foundation
& Trust
Governed approvals and outputs
Qualified core business pilot
Integration discovery in parallel
EXIT GATE
Pilot and controls accepted
NEXT · PLANNED
MVP 2
Enterprise Integration
& Efficiency
First approved on-premises source
Collibra intake; Genie if qualified
Secure caching; measurable value
EXIT GATE
Integration and value gates passed
LATER · PLANNED
MVP 3
Advanced
Visualization
Decision-ready charts and drill-down
Governed reports and exports
Adoption-led user experience
EXIT GATE
Safe sharing and adoption proven
AT EVERY MILESTONE
Security • Data trust • Answer quality • Performance • Cost • Adoption
Notes: The original three executive milestones are preserved; the second is renamed Enterprise Integration & Efficiency. This is proposed delivery packaging, not a renumbering of engineering phases. MVP 1 integrates the accepted foundation and pending 2F/2G trust controls. Genie feasibility and on-premises access discovery may run alongside it; Collibra ownership and metadata contracts belong with Phase 2F.3. Targeted runtime integration follows in engineering Phase 3 / proposed MVP 2 only after readiness and value gates. Genie is conditional, not guaranteed. An on-premises connector may move into MVP 1 only if essential to the approved pilot. Efficiency work spans later engineering phases; advanced visualization aligns with Phase 8. No milestone date or deployment is asserted.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S6] Owner-supplied conversation and previous roadmap photographs. Three executive milestones and green/white design direction. Application-owned entity authorization; service-identity source access; no mirrored user ACLs; governed semantics, templates and cache design. Photos are visual/reference material, not evidence of delivery or measured ROI.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 6
NEXT DELIVERY SEQUENCE
askalpha
Advance the core and integration discovery in parallel.
Proposed next actions; agree scope, ownership and capacity before setting delivery dates.
askalpha | executive update | September 2026
Basis: S3, S4, S7
06
1
Confirm the
baseline
Verify integration evidence and preserve accepted behavior.
ENGINEERING
2
Approve meaning
and change policy
Name semantic owners and define renewal and change rules.
PRODUCT + GOVERNANCE
3
Deliver governed
outputs
Use approved definitions and versioned templates.
ENGINEERING + DATA OWNERS
4
Qualify the
business pilot
Test answer quality, access and operating readiness.
BUSINESS + QA + OPERATIONS
IN PARALLEL
Genie feasibility • On-premises access • Collibra metadata contract
DELIVERY CADENCE
Two-week working demos proposed; release only when the required gates are met.
Notes: REVISION: The four core-delivery steps remain intact. Parallel work is bounded discovery: one Genie domain comparison, one on-premises source/access feasibility study and one Collibra metadata contract. Do not postpone the SQL-based governed pilot for optional integrations. Return an owner-backed go/no-go recommendation before runtime implementation.
PRIOR SLIDE CONTEXT (retained where not superseded)
This is a proposed executive work sequence based on the 1 September impact report, not authorization to change code or a dated plan. Detailed engineering sequence: reverify current baseline; close 2F.2 policy; certified semantic objects in 2F.3; template contracts and deterministic formatting in 2F.4; relationship impact only after governed evidence; hardening; controlled publish/rollback. AI formatting is optional and should stay disabled until approved. Delivery cadence comes from the supplied roadmap and must be agreed against capacity. Core work can proceed while integration approvals are resolved; an unapproved path cannot be used for a production pilot.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. ChatGPT Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Lifecycle, approval policy, certified meaning, templates, evidence-gated relationships and acceptance conditions.
[S6] Owner-provided conversation and roadmap photographs. Preserves three delivery milestones: Foundation & Trust; Scale & Efficiency; Advanced Visualization. Latest owner direction: application-owned entity authorization with Managed Identity source access and no user-ACL synchronization; early and post-plan caching; Semantic Registry business authority; deterministic output routing; Genie future evaluation. Two-week demos are a proposed cadence, not committed release dates.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 7
MVP 2 · EFFICIENCY TRACK
askalpha
Keep performance and cost measurable as coverage grows.
Targeted integration and efficiency are complementary—not automatic capacity commitments.
askalpha | executive update | September 2026
Evidence: S3, S5–S7
07
Reuse authorized
answers
Early lookup before AI planning.
A second cache for precise results.
Only small, bounded payloads.
Prepare common
questions
Prioritize patterns from usage.
Curate approved questions and summaries.
Release changes under review.
Publish with
control
Governed onboarding and rollback.
Named business and data owners.
Visible cost and performance.
~5 TB+
Source-data planning context—not cache size or proven capacity.
Keep large queries on the source platform; benchmark representative peak usage.
VALUE GATE
Measure response time, cost per answer and cache benefit before expanding capacity.
Notes: REVISION: Efficiency is one track within Enterprise Integration & Efficiency. No additional infrastructure or cache product is selected. Early-cache matching must be deterministic before any LLM call, include exact request parameters and authorization context, and validate entry eligibility. If a cache returns only a plan, source execution is still required; only an eligible result hit can skip the data query.
PRIOR SLIDE CONTEXT (retained where not superseded)
Two planned caches serve different purposes: an early request/template lookup must use deterministic information available before an AI call; the post-plan result cache may use a semantic plan hash. No current cache delivery is asserted. Safe keys need scope, exact request/template parameters and context, registry/recipe/template/policy/freshness identity and output semantics. Authorization precedes lookup. Cached results must be revalidated for scope and policy where applicable; a source revocation policy must be defined rather than assuming cache access bypasses platform controls. Approximately 5 TB or more is owner-provided planning context, not tested capacity. Monthly curated release is a working direction, not mandatory daily automation.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S5] Architecture and roadmap update, updated 26 Aug 2026: file_00000000a02081fd918c3632e0a5a902. Assumption and decision log: file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution and bounded results; scale qualification remains later work.
[S6] Owner-provided conversation and roadmap photographs. Preserves three delivery milestones: Foundation & Trust; Scale & Efficiency; Advanced Visualization. Latest owner direction: application-owned entity authorization with Managed Identity source access and no user-ACL synchronization; early and post-plan caching; Semantic Registry business authority; deterministic output routing; Genie future evaluation. Two-week demos are a proposed cadence, not committed release dates.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 8
STRATEGIC INTEGRATIONS
askalpha
Three integrations address three different business needs.
All have high strategic value; first implementation follows pilot demand and readiness.
askalpha | executive update | September 2026
Basis: S2–S7, W1–W3
08
INTEGRATION
WHY IT MATTERS
PROPOSED TIMING
DECISION REQUIRED
Databricks
Genie
Reuse analytics capability;
avoid duplicate development.
MVP 1: evaluate one domain.
MVP 2: integrate if qualified.
Sponsor a
comparative pilot.
On-premises
databases
Reach selected data without
a mandatory cloud migration.
MVP 1: select source and access path.
MVP 2: first targeted connector.
Name use case
and source owner.
Collibra
Reuse approved definitions;
reduce manual metadata upkeep.
MVP 1: ownership and metadata contract.
MVP 2: read-only ingestion and refresh.
Assign metadata
and API owners.
A required on-premises source may enter MVP 1 only when the approved pilot cannot proceed without it.
SEQUENCING RULE
Start discovery early; commit to integration only after a bounded business and control test.
Notes: These are three proposed integration workstreams with different roles: Genie provides a candidate analytics route; on-premises connectors extend data access; Collibra provides governed metadata. They are not substitutes for one another. Current SQL support remains unchanged. The three integration scopes are proposed, not active dependencies. Engineering Phase 3 is the integration phase, not executive MVP 3. Provider-native access and approval prerequisites must be verified. No user-permission synchronization is introduced.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W1] Microsoft Learn: Use the Genie Agents API. https://learn.microsoft.com/en-us/azure/databricks/genie-agents/conversation-api . Checked 9 Sep 2026. The API supports embedding conversational analytics; quality still depends on curated context and testing. API authorization and data/warehouse permissions must be confirmed for the chosen enterprise identity pattern.
[W2] Microsoft Learn: Connect to external databases and catalogs. https://learn.microsoft.com/en-us/azure/databricks/query-federation/ . SQL Server: https://learn.microsoft.com/en-us/azure/databricks/query-federation/sql-server . Oracle: https://learn.microsoft.com/en-us/azure/databricks/query-federation/oracle . Checked 9 Sep 2026. External database access is also possible through Databricks federation; the askalpha proposal is platform choice, not exclusive connectivity or guaranteed lower cost.
[W3] Collibra developer documentation: APIs https://developer.collibra.com/api ; Output Module https://developer.collibra.com/api/guides/output-module . Checked 9 Sep 2026. Supported APIs can retrieve assets, attributes and relationships. Availability, populated metadata, credentials, permissions and enterprise approval remain to be confirmed in the relevant environment.

## Slide 9
DATABRICKS GENIE · EVALUATE NOW
askalpha
Evaluate Genie now; adopt only where it proves value.
Potential value: reuse Databricks analytics while preserving the askalpha experience and controls.
askalpha | executive update | September 2026
Basis: S3, S7, W1
09
HIGH STRATEGIC VALUE
MVP 1: ASSESS → MVP 2: CONDITIONAL
Engineering integration: Phase 3
VALUE
Reduce duplicate analytics development.
Keep product-level access and audit.
FIRST TEST
One curated domain and agreed questions.
Compare direct SQL and Genie end to end.
GO / NO-GO GATE
Quality and pre-execution access isolation.
Latency, total cost and support ownership.
askalpha
Access • Semantics • Audit
Selected Genie domain
Candidate analytics provider
Governed data
Approved Databricks data scope
Release gate: prove end-user scope is enforced before Genie executes—not only when results return.
LEADERSHIP ASK
Sponsor one measured comparison; do not make Genie a dependency of the core pilot.
Notes: Proposed, not started or approved: assess Genie on one curated Databricks-resident domain using the same golden questions and authorization scopes as the direct path. The API offers an embedding route, but the vendor capability is not evidence of enterprise deployment or answer quality. A Genie request may execute queries; wrapping the returned answer in an application check is not sufficient. With shared workload identity, an approved restricted domain/object boundary or equivalent pre-execution control must enforce the end user’s permitted entity scope. No continuous user-ACL mirror is introduced. Reject or defer the candidate if the chosen provider cannot satisfy that boundary. Compare accuracy, evidence, response time, query cost, model cost, operations and maintainability before recommending rollout. Timing is MVP 1 assessment, conditional MVP 2 implementation via engineering Phase 3.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W1] Microsoft Learn: Use the Genie Agents API. https://learn.microsoft.com/en-us/azure/databricks/genie-agents/conversation-api . Checked 9 Sep 2026. The API supports embedding conversational analytics; quality still depends on curated context and testing. API authorization and data/warehouse permissions must be confirmed for the chosen enterprise identity pattern.

## Slide 10
KEY FACTOR COMPARISON
askalpha
askalpha vs Genie: compare business fit, not feature counts.
Documented askalpha delivery vs. published Genie capabilities—not equal deployment readiness.
askalpha | executive update | September 2026
Basis: project evidence + official docs · 9 Sep 2026
10
DECISION FACTOR | askalpha | DATABRICKS GENIE
Delivery & ownership | Accepted SQL pilot; the team owns product expansion and ongoing support. | Packaged analytics; domain curation, testing and operations are still required.
Cloud & on-premises | Azure-based today; direct on-premises adapters are planned—not proven deployed. | Cloud-hosted; supported external data via federation. Not a fully offline service.
Performance | No representative end-to-end benchmark; early request/result caching remains planned. | AI + warehouse latency: benchmark the same questions and data in warm and cold states.
Scale: ~5 TB+ | Planning context—not qualified capacity. Large queries stay on the source platform. | Warehouse scaling is available; validate burst load, scan cost and capacity limits.
Semantics & change | Versioned registry, an approved calculation and field-level change protection. | Curated definitions, trusted SQL, benchmarks and version-controlled configuration.
Authorization | App-owned entity scope + source service identity; no user-permission synchronization. | Native user-level catalog controls; service API integration must prove scope isolation.
Economic fit | Potential value in custom controls and independent access to multiple data platforms. | Strong Databricks-native option; temporary human AI promotion is not full ownership cost.
DECISION LENS
Genie is a strong native option; askalpha must prove its cross-platform value.
Notes: PURPOSE AND INTERPRETATION
This slide compares documented askalpha delivery with the published Genie Agents analytical product (formerly Spaces), not Genie Code. Vendor functionality is not evidence that it is approved or deployed in this organization. No new repository, deployment, latency or capacity test was performed for this presentation. The recommendation is an analyst assessment, not an approved procurement decision.
HOW TO READ THE FACTORS
1. Delivery and ownership. Internal records document the accepted foundation through Phase 2E: bounded SQL access, entity permissions, versioned registry and plans, one approved recipe and field-change protection. The 1 September architecture review reports Phase 2F.1 implementation/review but leaves final merge and activation subject to re-verification. New integrations and distributed request/result caching are not counted as delivered. Both choices still require semantic preparation, evaluation and operational ownership.
2. Cloud and on-premises. askalpha currently depends on Azure application/model services. A provider-neutral data-access contract does not establish full multi-cloud portability. Direct on-premises adapters are a planned opportunity, with network, supported workload identity, source capacity and read-only scope still to qualify. Genie uses Unity Catalog-registered data, including foreign tables; federation can reach supported external databases without requiring an initial copy of all their data. Databricks and remote-source execution/network costs may both apply. Neither option in this comparison is a fully offline on-premises deployment.
3. Performance. No end-to-end winner is established. Compare p50/p95 time to an accepted answer using the same questions, data snapshot and permissions. Break down authentication, metadata, AI, queue/cold start, SQL and formatting. Separate warm/cold compute and caches. Warehouse startup is not an answer-time SLA.
4. Scale. Approximately 5 TB or more is planning context, not evidence of qualified capacity. Evaluate scanned bytes, result limits, query mix, peak queueing, autoscaling and cost. Thirty signed-in or active users are not necessarily thirty simultaneous queries. Test burst concurrency separately. No table-count or throughput superiority is asserted here.
5. Business meaning and change. askalpha has documented version/dependency checks. Genie also offers curated semantics, trusted SQL, benchmarks and configuration deployment/versioning. Compare answer-level provenance and response to governed changes; do not claim semantic governance or caching is unique to askalpha.
6. Authorization. The owner-selected askalpha MVP keeps end-user entity permissions in the application and source access under a workload identity. It does not mirror every user's source ACL. Genie native user access applies Unity Catalog permissions; a shared-service API route must preserve the user's scope before execution. A prompt instruction or output filtering alone does not establish that isolation. No ACL synchronization project is proposed.
7. Economic fit. Evaluate remaining engineering, maintenance and operations as well as compute and AI. Distinguish native human use from service-principal use. Do not treat temporary promotions, existing source capacity or an API wrapper as permanently free.
DECISION TEST
Use a bounded representative pilot, including month-end where relevant. Measure correct/accepted-answer rate, latency, denied-before-execution behavior, source workload, metered AI and SQL costs, and forward support effort. askalpha's proposed differentiator is selective direct multi-platform access and organization-specific control, not a proven advantage on every metric.
SOURCES / CHECKED 9 SEPTEMBER 2026
[P1] askalpha accepted current-state record, verification dated 26 August 2026; Library file ID file_00000000794881fdbf5e728f1de30ebd.
[P2] ARCHITECTURE_DELTA_IMPACT_REPORT.md, 1 September 2026; Library file ID file_00000000d9c081f6a266f8bdbf5b513f.
[P3] Attached cost/comparison workbook: askalpha_vs_Genie_Executive_Cost_Model_2026-09-09.xlsx; Comparison and Benchmark_Plan worksheets.
[W1] Genie Agents concepts: https://learn.microsoft.com/en-us/azure/databricks/genie-agents/concepts
[W2] Genie curation and configuration versioning: https://learn.microsoft.com/en-us/azure/databricks/genie-agents/best-practices
[W3] Genie API and identity: https://learn.microsoft.com/en-us/azure/databricks/genie-agents/conversation-api
[W4] External database federation: https://learn.microsoft.com/en-us/azure/databricks/query-federation/
[W5] SQL warehouse behavior/types: https://learn.microsoft.com/en-us/azure/databricks/compute/sql-warehouse/warehouse-types
[W6] Genie billing: https://learn.microsoft.com/en-us/azure/databricks/genie/monitor-cost

## Slide 11
COST COMPARISON · ILLUSTRATIVE MONTHLY MODEL
askalpha
Operating cost is only one part of the investment decision.
USD planning scenario—not a vendor quote, tested capacity or full total cost of ownership (TCO).
askalpha | executive update | September 2026
Basis: cost workbook + pricing docs · 9 Sep 2026
11
10,000 questions / month | 220 billed cluster-hours | ~5 TB source | No early-cache savings assumed
MONTHLY COST / USD | askalpha direct | Genie human UI* | askalpha + Genie service API
Query compute (shared budget) | $1,760 | $1,760 | $1,760
App + control services (budget) | $600 | $0** | $600
AI usage | $385 | $0* | G — metered
OPERATING SUBTOTAL | $2,745 | $1,760* | $2,360 + G
ASKALPHA MODEL CALCULATION
8,000 input + 1,500 output
tokens per question
GPT-5.2 reference pricing
+ 10% retry / repair allowance
$385 / month
$0.0385 per question
Public API rate—not an Azure quote.
Sensitivity only: at G = $500/month, the hybrid subtotal is $2,860. This is not a quoted Genie tariff.
* Human Genie AI promotion ends 31 Jan 2027; service principals are billed. Query compute is separate.
** No custom app in native UI. All totals exclude people, delivery work, storage, network and security/DR.
INVESTMENT RULE
Compare full forward TCO per accepted answer; replace assumptions with metered usage.
Notes: CALCULATION METHODOLOGY — READ BEFORE USING AS A BUDGET
All monetary figures are USD per month. This is an illustrative operating subtotal for the standard question-and-answer path, not a supplier quotation, a proven 5-TB design, an actual invoice, or a full TCO. It compares the attached workbook's scenarios without changing its inputs. askalpha and Genie do not necessarily use the same underlying language model. The benchmark is a like-for-like business workload, not claimed model equivalence.
1. INPUTS AND EXACT WORKBOOK REFERENCES
Workbook: askalpha_vs_Genie_Executive_Cost_Model_2026-09-09.xlsx.
- Inputs!B5: 10,000 total business questions/month, including repeated questions/follow-ups. This is an assumption, not observed demand or the count of internal API calls.
- Inputs!B6: 5 TB source-data context. Inputs!B7: 30 peak active users. Neither proves hardware sizing, query concurrency or latency.
- Inputs!B8:B10: 22 working days x 10 active hours/day = 220 billed cluster-hours. Count all billed clusters, startup/idle time and scale-out; multiple clusters increase total hours.
- Inputs!B11: $8 effective all-in compute-hour budget. This is a placeholder, NOT a published price for a particular SQL Warehouse SKU, size or Azure region.
- Inputs!B12:B13: 8,000 input tokens and 1,500 billed output tokens per successful uncached business question, aggregated across its model calls. Include reasoning tokens where charged; this is not only the visible answer length.
- Inputs!B14:B15: public OpenAI direct GPT-5.2 API reference prices of $1.75 per million input tokens and $14 per million output tokens, checked 9 September 2026. These are NOT the organization's Azure OpenAI contract, a claim of the active model, or a recommendation to change deployment. Replace with the approved regional deployment rate.
- Inputs!B16: 10% approximate proportional allowance for retries/repair. Replace this with all actual model calls/tokens; a flat allowance is not a measurement.
- Inputs!B17: 0% deployed early-result-cache hit benefit assumed. Existing in-process metadata caching is different. No provider prompt-caching discount or batch discount is assumed.
- Inputs!B18:B20: $250 app/UI/API + $250 search/metadata + $100 registry/audit = $600. These are unverified budgets, not priced HA, WAF, SIEM or DR plans.
- Inputs!B21: $600 hybrid app overhead, held equal for illustration.
- Inputs!B22: $0.05/question is a hypothetical Genie service-principal AI sensitivity input, NOT a Databricks published tariff.
- Inputs!B31: $0 extra askalpha AI/API calls on the hybrid path in the base case. Add actual double-planning/formatting calls when present.
2. ASKALPHA MODEL FORMULA
Input cost/question = 8,000 x $1.75 / 1,000,000 = $0.014.
Output cost/question = 1,500 x $14 / 1,000,000 = $0.021.
Base model cost/question = $0.014 + $0.021 = $0.035.
With retry/repair allowance = $0.035 x 1.10 = $0.0385.
Monthly AI = 10,000 x $0.0385 = $385.
Workbook reconciliation: Monthly_Cost!B8 = $385; B13 = $0.0385; B14 = $385.
A complete measured cost substitutes the sum of all charged input/output/tool calls rather than multiplying one nominal request price.
3. SHARED COMPUTE AND APPLICATION BUDGETS
Compute = 22 x 10 x $8 = $1,760/month.
App/control = $250 + $250 + $100 = $600/month.
Holding compute constant isolates app/AI arithmetic. It does NOT prove equal query counts, execution time, scan volume or required cluster size across the alternatives. A 5-TB source size is not multiplied by a per-question rate.
4. OPTION TOTALS
askalpha direct = $1,760 + $600 + $385 = $2,745/month (Monthly_Cost!B10).
Genie native human UI during the stated promotion = $1,760 query compute + $0 custom app + $0 eligible Genie AI = $1,760/month (Monthly_Cost!C10). Zero custom-app cost is not zero domain curation, governance, support or enterprise cost.
askalpha + Genie service API = $1,760 + $600 + G + H = $2,360 + G + H. G is metered Genie AI; H is any extra hybrid app AI/API cost (assumed zero in the displayed subtotal).
For sensitivity only: G = 10,000 x $0.05 = $500, giving $2,860/month (Monthly_Cost!D10).
Other G scenarios: $100 / $1,500 / $3,000 -> hybrid subtotals $2,460 / $3,860 / $5,360, with all other budgets unchanged.
AI-only parity in this example is G = $385/month, or $0.0385/question, not full-TCO or quality parity.
5. GENIE BILLING AND HOW TO REPLACE G
Official policy checked 9 September 2026: eligible human Genie Agents/One use is free through 31 January 2027; service-principal usage is billed. SQL/query compute remains separate. The endpoint alone does not determine eligibility: record the actual run-as identity.
Obtain G from system.billing.usage joined to the valid regional SKU/time/currency in system.billing.list_prices. Filter billing_origin_product='GENIE', usage_metadata.genie.surface='GENIE_AGENTS' and the intended service identities; exclude GENIE_FREE_USAGE. Sum usage_quantity x applicable effective_list unit price, then reconcile contract terms and invoice adjustments. Do not double-apply the temporary 25% billed-usage promotion: the documentation says metered billed usage already includes it. Query-compute records must be budgeted separately without double-counting.
Do not annualize the human promotional zero as a perpetual rate. Price the months after the promotion using then-applicable allowances, observed usage and contract terms. The workbook correctly leaves the full year-one TCO incomplete until missing inputs are supplied.
6. EXCLUSIONS, FAIRNESS AND SENSITIVITY
Not included: remaining product/connector engineering, migration, source storage/licensing, private network/egress, security/compliance/MRM, production resiliency, backup/DR, monitoring retention, business curation, support and enterprise overhead. These apply to all three options, in different amounts. Sunk development is not charged again in a forward investment comparison.
TCO = remaining one-time delivery + future runtime + data/semantic preparation + testing/governance + people/operations + network/security/recovery.
An illustrative 40 extra support hours/month x $100/hour = $4,000/month or $48,000/year. This is sensitivity, not actual staffing or a disclosed labor rate.
An illustrative future 50% eligible early-cache hit rate saves only $192.50/month in model cost at this volume; a $200 cache budget would give -$7.50/month token-only savings if compute hours stay unchanged. Do not assume caching reduces an always-on warehouse bill.
For direct on-premises use, the app/model subtotal alone is $985; source compute/licenses, network and adapter work must still be added. It is not a total on-premises cost.
7. EXECUTIVE DECISION
Compare full forward cost per correct, accepted answer under a common representative workload. Record warm/cold p50/p95 latency, correctness, burst concurrency, scan cost, service identity, actual tokens/DBUs and support effort. Neither operating subtotal establishes a procurement winner or validates 5-TB performance.
SOURCES
[C1] Attached workbook, Inputs, Monthly_Cost, Sensitivity, TCO_Gaps and Sources tabs; prepared 9 September 2026. Values read and arithmetic rechecked for this slide.
[W1] GPT-5.2 public direct API pricing: https://developers.openai.com/api/docs/models/gpt-5.2
[W2] Genie promotion, identities and metered usage: https://learn.microsoft.com/en-us/azure/databricks/genie/monitor-cost
[W3] Query compute is separate from free AI use: https://www.databricks.com/product/pricing/genie
[W4] Genie API identity patterns: https://learn.microsoft.com/en-us/azure/databricks/genie-agents/conversation-api
[P1] Project architecture delta review dated 1 September 2026; planned cache/provider capabilities are not treated as live savings.
Public sources checked 9 September 2026. Finance must replace illustrative compute/app budgets and model reference rates with approved regional/contract values.

## Slide 12
ON-PREMISES DATA · BUSINESS-LED
askalpha
Prove independence with one on-premises use case.
Potential value: reach approved data in place without forcing every request through Databricks.
askalpha | executive update | September 2026
Basis: S2, S5, S7, W2
12
HIGH VALUE · DEMAND-LED
MVP 1: DISCOVER → MVP 2: FIRST SOURCE
A TARGETED DIRECT PATH
askalpha
User scope + governed question
Source adapter
Approved network + service identity
One on-premises source
Read-only views • bounded queries
Illustrative target; not a confirmed live connection.
01
Select the first source
One SQL Server or Oracle use case—not all databases.
02
Approve access and workload
Validate network, service identity and source capacity.
03
Prove the operating model
Bound queries; test peak load, cost and safe failure.
Existing SQL support does not prove on-premises connectivity. Source and network costs still apply.
LEADERSHIP ASK
Choose the first source and accountable owner; bring it forward only if the pilot requires it.
Notes: Proposed sequence: confirm the business question and one required on-premises database during MVP 1; deliver a source-specific read-only adapter and tested connectivity in engineering Phase 3 / MVP 2. A single essential source may be moved into MVP 1 by explicit scope and readiness approval, not by making every on-premises platform a prerequisite. Managed Identity is preferred where actually supported; do not assume all on-premises SQL Server or Oracle systems accept it. IAM must approve the source-appropriate workload identity, secret handling where needed, network and server configuration. Service identity only defines the application envelope; askalpha continues to enforce end-user entity scope before execution. Execute heavy analytical work on an approved source/read replica and return bounded results; assess source workload impact, licenses, network and operations as costs. Databricks federation also supports external SQL Server and Oracle access. The differentiator proposed here is the option of direct execution without a mandatory Databricks intermediary, not a claim that Genie/Databricks cannot access external data or that this route is free.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W2] Microsoft Learn: Connect to external databases and catalogs. https://learn.microsoft.com/en-us/azure/databricks/query-federation/ . SQL Server: https://learn.microsoft.com/en-us/azure/databricks/query-federation/sql-server . Oracle: https://learn.microsoft.com/en-us/azure/databricks/query-federation/oracle . Checked 9 Sep 2026. External database access is also possible through Databricks federation; the askalpha proposal is platform choice, not exclusive connectivity or guaranteed lower cost.

## Slide 13
COLLIBRA · GOVERNED METADATA REUSE
askalpha
Reuse definitions without creating a competing catalog.
Potential value: reuse approved meaning, ownership and classifications as the data estate grows.
askalpha | executive update | September 2026
Basis: S3, S4, S7, W3
13
HIGH GOVERNANCE VALUE
MVP 1: CONTRACT → MVP 2: READ-ONLY INTEGRATION
Collibra
Approved metadata
and named owners
Validate & map
Check evidence;
publish under review
Semantic Registry
Versioned runtime
semantic snapshot
Plans & templates
Reference approved
IDs and versions
Read-only metadata intake; not analytical-data movement and not a per-question API dependency.
AGREE IN MVP 1
Owners and approved scope
Assign definition owners;
agree mapping and freshness.
DELIVER IN MVP 2
Read-only metadata intake
Validate and publish snapshots;
monitor refresh failures.
KEEP OWNERSHIP CLEAR
One runtime semantic contract
Preserve source and version;
templates only reference them.
LEADERSHIP ASK
Confirm metadata and API owners. Metadata integration is not user-permission synchronization.
Notes: Proposed Collibra boundary: the enterprise owner decides which approved definitions and governance attributes originate in Collibra or another system of record. askalpha publishes a validated, versioned canonical runtime snapshot; it must not become a competing authoring authority for imported definitions. Templates reference semantic IDs and versions, not re-encoded KPIs. The Collibra API/Output Module can retrieve relevant assets, attributes and relationships. Actual enterprise metadata population, API access, authentication, approval and freshness remain to be verified. Contract and ownership work can be included in Phase 2F.3 during MVP 1. Read-only adapter, refresh and operational integration are separate Phase 3 / proposed MVP 2 work; avoid expanding the Phase 2F.1 evaluator. Start with one domain and scheduled/controlled refresh rather than a per-question catalog call. Preserve provenance, reject conflicting required evidence, and define stale/unavailable behavior. This is governance metadata intake, not an ACL synchronization engine, and metadata never grants access.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W3] Collibra developer documentation: APIs https://developer.collibra.com/api ; Output Module https://developer.collibra.com/api/guides/output-module . Checked 9 Sep 2026. Supported APIs can retrieve assets, attributes and relationships. Availability, populated metadata, credentials, permissions and enterprise approval remain to be confirmed in the relevant environment.

## Slide 14
PILOT SUCCESS MEASURES
askalpha
Prove business and integration value before wider rollout.
Use the same approved questions and access scope for comparative tests.
askalpha | executive update | September 2026
Basis: S2, S3, S5–S7
14
FOCUSED PILOT
Focused scope.
Measure value.
Business sponsor
Selected data products
Approved test questions
Baseline and review date
Business impact
Time to a trusted answer and reporting effort
compared with the existing process.
Answer quality
Agreement with approved results; preserve
values, dates, sources and warnings.
Access & privacy
No unauthorized disclosure in the agreed tests;
use only approved model payloads.
Operational fit
Response time, freshness, source impact and total cost
for each candidate path under representative peak use.
PILOT EXIT
Expand, adjust or pause based on evidence—not on feature count alone.
Notes: REVISION: Add integration-specific measurement to the pilot scorecard. Compare Genie and direct execution only on equivalent questions, data and permitted scope. For on-premises, include source workload and network impact. For Collibra, measure metadata completeness for the chosen scope, freshness and manual upkeep avoided. Do not claim measured benefits until baselines and tests exist.
PRIOR SLIDE CONTEXT (retained where not superseded)
All measures on this slide are recommendations and not achieved outcomes. No measured productivity gain, reporting reduction, adoption or ROI is available in the reviewed evidence. Peak concurrency is to be agreed for aggregate scope; previous use-case estimates must not be presented as validated enterprise capacity. A pilot acceptance test is not a universal guarantee of security or reliability. Existing regulated/scheduled reports continue unless their owners approve rationalization. The pilot complements those reporting channels rather than committing to replacing them.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S2] Phase journey and manager summary, updated 26 Aug 2026. ChatGPT Library file ID file_00000000e57881fda2f0c1cc493a8779. Management roadmap and feature map, updated 26 Aug 2026: file_00000000212881fd8df615c438684075.
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S5] Architecture and roadmap update, updated 26 Aug 2026: file_00000000a02081fd918c3632e0a5a902. Assumption and decision log: file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution and bounded results; scale qualification remains later work.
[S6] Owner-provided conversation and roadmap photographs. Preserves three delivery milestones: Foundation & Trust; Scale & Efficiency; Advanced Visualization. Latest owner direction: application-owned entity authorization with Managed Identity source access and no user-ACL synchronization; early and post-plan caching; Semantic Registry business authority; deterministic output routing; Genie future evaluation. Two-week demos are a proposed cadence, not committed release dates.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 15
DECISIONS REQUIRED
askalpha
Six decisions turn integration options into a delivery plan.
Confirm the priorities and accountable functions; implementation remains separately gated.
askalpha | executive update | September 2026
Basis: S3–S7 · proposed decisions
15
DECISION
LEADERSHIP ACTION
ACCOUNTABLE FUNCTIONS
01
Pilot focus
& capacity
Approve pilot scope and bounded integration discovery;
confirm capacity and success measures.
Business sponsor
& Product
02
Genie
evaluation
Choose one domain and agreed comparison criteria;
sponsor the assessment before any rollout decision.
Product
& Architecture
03
On-premises
priority
Name the first use case and source owner;
confirm the access path and workload budget.
Data owners
& Platform
04
Collibra
& semantics
Name definition and API owners; approve the
read-only metadata contract and refresh expectations.
Data Governance
& Platform
05
Controls
& privacy
Agree approval/change policies and permitted AI use;
keep result-formatting AI off until approved.
Governance / Product
& Privacy / Security
06
Operations
& release
Set service and cost goals, acceptance evidence
and the pilot go/no-go authority.
Architecture
& Operations
RECOMMENDED ASK
Endorse the sequence and assign owners; commit delivery dates only after readiness is confirmed.
Notes: The new rows explicitly request decisions for Genie, on-premises connectivity and Collibra, not just general platform approval. These are accountable-function proposals; no named owner is assigned by this deck. Core business approval/renewal/change policy, AI privacy, operational targets and release evidence remain required. Do not interpret the six decisions as blanket production approval, an open-ended connector program or a funding commitment. No quantified spend or fixed date is invented. Entity-level application authorization and service-identity access remain the working MVP model with no user-ACL synchronization.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 16
APPENDIX · DELIVERY CONFIDENCE
askalpha
Capability status: what is delivered versus still ahead.
Architecture decisions are not evidence of production activation.
askalpha | executive update | September 2026
Evidence: S1–S5
16
DOCUMENTED DELIVERY
Accepted foundation through 2E
Secure SQL access; governed registry and plans; one approved calculation;
field-change protection; provider-neutral source boundary.
REPORTED IMPLEMENTATION
Lifecycle classification (2F.1)
Implementation and independent review are reported. Current merge /
activation state has not been reverified for this presentation.
WORKING DESIGN DECISIONS
Clear ownership and safe extensibility
Registry owns business meaning; application owns user scope; no ACL sync;
fixed formatting rules; early plus result-cache design.
PLANNED / CONDITIONAL
Broader operational and user capabilities
Certified catalog/templates; caching; Genie assessment, on-premises and Collibra
integrations; self-service and exports. Runtime rollout remains approval-gated.
IMPORTANT DISTINCTION
Metadata snapshot caching exists; request/result-cache rollout is still planned.
Notes: REVISION: Planned integration opportunities are now timed, not reclassified as implemented. Genie remains a candidate and may fail its evaluation. On-premises access and Collibra API readiness are not established by the current SQL foundation. Source/version metadata provenance complements the runtime Registry authority; no competing definition store is proposed.
PRIOR SLIDE CONTEXT (retained where not superseded)
This status matrix reconciles the historical 26 August current-state record with the 1 September impact report. It does not assign a percentage completion or infer any deployment. 2F.1 evidence concerns a classification-only evaluator, default OFF; this does not mean approved operational policy is active. The design decisions are owner-level working program direction, not blanket enterprise approval. Treat every new provider and optional AI result boundary as separately qualified.
EVIDENCE AND STATUS DISCIPLINE
Completed means documented engineering delivery in the stated scope, not enterprise production rollout. No live repository or deployment check was performed for this presentation. Roadmap targets and benefits are not measured achievements.
SOURCES
[S1] Authoritative current-state record, updated 26 Aug 2026. ChatGPT Library file ID file_00000000794881fdbf5e728f1de30ebd. Foundation through 2E; one pilot dataset/recipe; 199 governed fields; bounded evidence and successful workflows.
[S2] Phase journey and manager summary, updated 26 Aug 2026. ChatGPT Library file ID file_00000000e57881fda2f0c1cc493a8779. Management roadmap and feature map, updated 26 Aug 2026: file_00000000212881fd8df615c438684075.
[S3] Architecture Delta Impact Report, 1 Sep 2026. ChatGPT Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Reports 2F.1 implementation and independent review, but current merge acceptance is REVERIFY_REQUIRED. Explicit semantic ownership, no ACL-sync MVP, planned two-stage caching and conditional AI formatting.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. ChatGPT Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Lifecycle, approval policy, certified meaning, templates, evidence-gated relationships and acceptance conditions.
[S5] Architecture and roadmap update, updated 26 Aug 2026: file_00000000a02081fd918c3632e0a5a902. Assumption and decision log: file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution and bounded results; scale qualification remains later work.
Design: user-supplied green-and-white executive and three-milestone roadmap screenshots. Native PowerPoint shapes and text; no screenshot content copied as delivery evidence.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S1] Authoritative current-state record, updated 26 Aug 2026. Library file ID file_00000000794881fdbf5e728f1de30ebd. Accepted foundation through 2E; one governed pilot dataset and calculation; 199 evidenced fields. Historical delivery evidence, not a live production check.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.

## Slide 17
APPENDIX · PHASE CROSSWALK AND EVIDENCE
askalpha
Executive milestones are not engineering phase numbers.
Proposed packaging of the existing roadmap—not renumbering or new delivery evidence.
askalpha | executive update | September 2026
Basis: S1–S7, W1–W3
17
EXECUTIVE MILESTONE
ENGINEERING ALIGNMENT
MVP 1
Foundation & Trust
Accepted foundation through 2E; 2F trust/lifecycle/templates and 2G controlled publishing. Integration discovery may run in parallel.
MVP 2
Enterprise Integration
& Efficiency
Phase 3: selected providers, Genie and metadata integration. Phases 4–7: safety, evaluation, performance and self-service.
MVP 3
Advanced Visualization
Phase 8: richer visualization, reports, downloads, exports and approved experience integrations.
Collibra contract: Phase 2F.3. Provider implementation: Phase 3.
An essential on-premises source may be brought forward by explicit pilot scope approval.
EVIDENCE BOUNDARY
Foundation record: 26 Aug 2026.
Impact report: 1 Sep 2026.
2F.1 final integration has not
been live-reverified here.
Vendor docs checked 9 Sep 2026;
enterprise readiness is not proven.
5 TB+ is planning context.
Dates, savings and scale are not promised.
REFERENCE DETAIL
Speaker notes retain source references, vendor links and the qualifications behind each slide.
Notes: Crosswalk is an executive presentation recommendation, not an approved technical renumbering. Existing engineering roadmap is preserved. Phase 2F.3 defines certified semantic contracts; integrating live Collibra and other provider APIs is separate Phase 3 work. Phase 3 also contains Databricks/provider work and the Genie coexistence boundary. Broader safety/evaluation/performance/self-service phases contribute to executive MVP 2; engineering Phase 8 supports executive MVP 3. Preparatory discovery does not require waiting for the end of MVP 1, but runtime activation still requires the relevant gates. Source evidence remains historical through accepted 2E with a 1 September 2F.1 review. No repository, deployment, service-access or environment check was conducted for this presentation. Vendor docs only support external feature feasibility. Approximately 5 TB or more is a planning context, not a demonstrated capacity.
EVIDENCE / STATUS
This is a presentation revision, not a live repository or deployment verification. Completed refers only to documented engineering delivery. Vendor capability does not establish enterprise readiness. Recommended timing and benefits are not approved launch commitments or measured outcomes.
REFERENCES
[S1] Authoritative current-state record, updated 26 Aug 2026. Library file ID file_00000000794881fdbf5e728f1de30ebd. Accepted foundation through 2E; one governed pilot dataset and calculation; 199 evidenced fields. Historical delivery evidence, not a live production check.
[S2] Phase journey and management roadmap, updated 26 Aug 2026. Library file IDs file_00000000e57881fda2f0c1cc493a8779 and file_00000000212881fd8df615c438684075. Engineering Phase 3: approved providers and Genie coexistence; Phases 4-7: safety, evaluation, performance and publishing; Phase 8: visualization and exports.
[S3] Architecture Delta Impact Report, 1 Sep 2026. Library file ID file_00000000d9c081f6a266f8bdbf5b513f. Phase 2F.1 implementation/review reported; final merge and activation require re-verification. Registry semantic authority, referenced templates, no user-ACL synchronization, optional AI formatting and planned early/result cache contracts.
[S4] Phase 2F Scope Discovery, 26 Aug 2026. Library file ID file_00000000c24c81fdbfea4ccb0f4e409b. Approval policy; certified semantics; output templates; governed relationship impact and independently reviewed slices.
[S5] Architecture/roadmap and decision log, updated 26 Aug 2026. Library file IDs file_00000000a02081fd918c3632e0a5a902 and file_00000000e3648230adcaafa37e6315c6. Approximately 5 TB or more is planning context; provider-side execution with bounded results. No enterprise scale qualification claimed.
[S6] Owner-supplied conversation and previous roadmap photographs. Three executive milestones and green/white design direction. Application-owned entity authorization; service-identity source access; no mirrored user ACLs; governed semantics, templates and cache design. Photos are visual/reference material, not evidence of delivery or measured ROI.
[S7] Owner-requested integration-roadmap revision in this conversation. Proposed timing: evaluate Genie alongside MVP 1 and conditionally integrate in MVP 2; discover on-premises access in MVP 1 and deliver one selected source in MVP 2, brought forward only if essential to the approved pilot; define Collibra metadata ownership/contracts in MVP 1 and implement read-only integration in MVP 2. MVP 2 is reframed as Enterprise Integration & Efficiency. These are recommended priorities, not environment approvals or dated commitments.
[W1] Microsoft Learn: Use the Genie Agents API. https://learn.microsoft.com/en-us/azure/databricks/genie-agents/conversation-api . Checked 9 Sep 2026. The API supports embedding conversational analytics; quality still depends on curated context and testing. API authorization and data/warehouse permissions must be confirmed for the chosen enterprise identity pattern.
[W2] Microsoft Learn: Connect to external databases and catalogs. https://learn.microsoft.com/en-us/azure/databricks/query-federation/ . SQL Server: https://learn.microsoft.com/en-us/azure/databricks/query-federation/sql-server . Oracle: https://learn.microsoft.com/en-us/azure/databricks/query-federation/oracle . Checked 9 Sep 2026. External database access is also possible through Databricks federation; the askalpha proposal is platform choice, not exclusive connectivity or guaranteed lower cost.
[W3] Collibra developer documentation: APIs https://developer.collibra.com/api ; Output Module https://developer.collibra.com/api/guides/output-module . Checked 9 Sep 2026. Supported APIs can retrieve assets, attributes and relationships. Availability, populated metadata, credentials, permissions and enterprise approval remain to be confirmed in the relevant environment.